## 87-763-RePlan-2022-06-07
Task Name | Duration | Start | Finish | Predecessors | Environment | Visual Flag | Include environment | Include Start Date | Include End Date | date for display | Visual Text | Visual Swimlane | Visual Track # Within Swimlane | Visual # Tracks To Cover | Format String | Done Format String | Text Layout | Assigned To | % Complete | Status | Comments
Financier Upgrade | 115d | 2022-06-01 | 2022-11-08 | [7 empty] | Financier Upgrade |  |  |  | Activity Green |  | Left
Environment Build and Management | 18d | 2022-06-01 | 2022-06-24 | [7 empty] | Environment Build and Management |  |  |  | Activity Green |  | Left
MGMT | 15d | 2022-06-06 | 2022-06-24 |  | MGMT | [5 empty] | MGMT | Environments | 1 |  | Activity Green |  | Left
Complete RDS Configuration | 15d | 2022-06-06 | 2022-06-24 |  | MGMT | TRUE |  |  |  |  | Complete RDS Configuration | Environments | 1 |  | Activity Green |  | Right
Web Help complete network routing configuration | 0 | 2022-06-24 | 2022-06-24 |  | MGMT | [5 empty] | Web Help complete network routing configuration | Environments | 1 |  | Milestone Blue |  | Left
Wait for Web Help to carry out configuration | 14d | 2022-06-06 | 2022-06-23 | 5FF | MGMT | [5 empty] | Wait for Web Help to carry out configuration | Environments | 1 |  |  |  | Left
Complete RDS configuration | 1d | 2022-06-24 | 2022-06-24 | 6 | MGMT | [5 empty] | Complete RDS configuration | Environments | 1 |  | Activity Green |  | Right
MGMT Environment Available for Testing | 0 | 2022-06-24 | 2022-06-24 | 7 | MGMT | [5 empty] | MGMT Environment Available for Testing | Environments | 1 |  | Milestone Blue |  | Right
ACPT | 10d | 2022-06-01 | 2022-06-15 |  | ACPT | [5 empty] | ACPT | Environments | 2 |  | Milestone Blue |  | Left
Complete tasks to switch from 9.0 to 9.8 | 10d | 2022-06-01 | 2022-06-14 | 11FF | ACPT | TRUE |  |  |  |  | Complete tasks to switch from 9.0 to 9.8 | Environments | 2 |  | Activity Red |  | Right
ACPT environment available | 0 | 2022-06-15 | 2022-06-15 |  | ACPT | [5 empty] | ACPT environment available | Environments | 2 |  | Milestone Blue |  | Left
PERF/PROD | 6d | 2022-06-10 | 2022-06-17 |  | PERF/PROD | [5 empty] | PERF/PROD | Environments | 3 |  | Activity Green |  | Left
Sign off of PERF/PROD Visio / Spec | 0 | 2022-06-10 | 2022-06-10 |  | PERF/PROD | [5 empty] | Sign off of PERF/PROD Visio / Spec | Environments | 3 |  | Milestone Blue |  | Left
Complete build of PERF/PROD (to WD deployment) | 5d | 2022-06-13 | 2022-06-17 | 13FS +1d | PERF/PROD | TRUE |  |  |  |  | Complete build of PERF/PROD (to WD deployment) | Environments | 3 |  | Activity Red |  | Right
PERF/PROD Environment Available for Testing | 0 | 2022-06-17 | 2022-06-17 | 14 | PERF/PROD | [5 empty] | PERF/PROD Environment Available for Testing | Environments | 3 |  | Milestone Blue |  | Left
All environments build complete | 0 | 2022-06-24 | 2022-06-24 | 8, 11, 15 | [6 empty] | All environments build complete | Environments |  |  | Milestone Blue |  | Left
Testing | 65d | 2022-06-15 | 2022-09-13 | [7 empty] | Testing | Testing / Implementation |  |  | Activity Green |  | Left
MGMT | 35d | 2022-06-27 | 2022-08-12 |  | MGMT | [5 empty] | MGMT | Testing / Implementation |  |  | Activity Green |  | Left
Carry out UAT (MGMT) | 35d | 2022-06-27 | 2022-08-12 | 8 | MGMT | TRUE |  |  |  |  | Carry out UAT (MGMT) | Testing / Implementation | 1 |  | Activity Green |  | Left
Testing (MGMT) Complete | 0 | 2022-08-12 | 2022-08-12 | 19 | MGMT | [5 empty] | Testing (MGMT) Complete | Testing / Implementation |  |  | Milestone Blue |  | Left
ACPT | 40d | 2022-06-15 | 2022-08-09 |  | ACPT | [5 empty] | ACPT | Testing / Implementation |  |  | Activity Green |  | Left
Carry out UAT (ACPT) | 40d | 2022-06-15 | 2022-08-09 | 11 | ACPT | TRUE |  |  |  |  | Carry out UAT (ACPT) | Testing / Implementation | 2 |  | Activity Green |  | Left
Testing (ACPT) Complete | 0 | 2022-08-09 | 2022-08-09 | 22 | ACPT | [5 empty] | Testing (ACPT) Complete | Testing / Implementation |  |  | Milestone Blue |  | Left
PERF/PROD | 62d | 2022-06-20 | 2022-09-13 |  | PERF/PROD | [5 empty] | PERF/PROD | Testing / Implementation |  |  | Activity Green |  | Left
Smoke/System Test (PERF/PROD) | 10d | 2022-06-20 | 2022-07-01 | 15 | PERF/PROD | TRUE |  |  |  |  | Smoke/System Test (PERF/PROD) | Testing / Implementation | 3 |  | Activity Red |  | Left
Carry out UAT (PERF/PROD) | 52d | 2022-07-04 | 2022-09-13 |  | PERF/PROD | [5 empty] | Carry out UAT (PERF/PROD) | Testing / Implementation |  |  | Activity Red |  | Left
UAT (PERF/PROD Part 1) | 10d | 2022-07-04 | 2022-07-15 | 25 | PERF/PROD | TRUE |  |  |  |  | UAT (PERF/PROD Part 1) | Testing / Implementation | 4 |  | Activity Red |  | Left
Non-Function Test (Early) | 6d | 2022-07-18 | 2022-07-25 | 27 | PERF/PROD | TRUE |  |  |  |  | Non-Function Test (Early) | Testing / Implementation | 3 |  | Activity Red |  | Right
UAT (PERF/PROD Part 2) | 20d | 2022-07-26 | 2022-08-22 | 28 | PERF/PROD | TRUE |  |  |  |  | UAT (PERF/PROD Part 2) | Testing / Implementation | 4 |  | Activity Red |  | Left
Non-Function (Late) | 6d | 2022-08-23 | 2022-08-30 | 29 | PERF/PROD | TRUE |  |  |  |  | Non-Function (Late) | Testing / Implementation | 3 |  | Activity Red |  | Right
UAT (PERF/PROD Part 3) | 10d | 2022-08-31 | 2022-09-13 | 30 | PERF/PROD | TRUE |  |  |  |  | UAT (PERF/PROD Part 3) | Testing / Implementation | 4 |  | Activity Red |  | Right
Testing (PERF/PROD) Complete | 0 | 2022-09-13 | 2022-09-13 | 31 | PERF/PROD | [5 empty] | Testing (PERF/PROD) Complete | Testing / Implementation | 5 |  | Milestone Blue |  | Left
All (non-prod) Testing Complete | 0 | 2022-09-13 | 2022-09-13 | 20, 23, 32 | [6 empty] | All (non-prod) Testing Complete | Testing / Implementation |  |  | Milestone Blue |  | Left
Go Live Readiness | 20d | 2022-09-14 | 2022-10-11 | 33 |  | TRUE |  |  |  |  | Go Live Readiness | Testing / Implementation | 5 |  | Activity Red |  | Left
Go Live (without Genesis Impact) | 0 | 2022-10-11 | 2022-10-11 | 34 |  | TRUE |  |  |  |  | Go Live (without Genesis Impact) | Testing / Implementation | 6 |  | Milestone Blue |  | Left
Estimated Genesis Impact | 20d | 2022-10-12 | 2022-11-08 | 35 |  | TRUE |  |  |  |  | Estimated Genesis Impact | Testing / Implementation | 1 | 6 | Genesis Impact
Go Live (with Genesis impact) | 0 | 2022-11-08 | 2022-11-08 | 36 |  | TRUE |  |  |  |  | Go Live (with Genesis impact) | Testing / Implementation | 6 |  | Milestone Red |  | Right
New FS Product | 200d | 2022-05-02 | 2023-02-03 | [7 empty] | New FS Product |  |  |  | Activity Green |  | Left
Plan Start | 0 | 2022-05-02 | 2022-05-02 | [7 empty] | Plan Start |  |  |  | Milestone Blue |  | Left
IOOP Business Design | 95d | 2022-05-02 | 2022-09-09 | [7 empty] | IOOP Business Design | IOOP Business |  |  | Activity Green |  | Left
Other business design activities (consumer duty etc) | 65d | 2022-05-02 | 2022-07-29 | 39 |  | TRUE |  |  |  |  | Other business design activities (consumer duty etc) | IOOP Business | 2 |  | Activity Green |  | Left
Carry out other design acitivities | 60d | 2022-05-02 | 2022-07-22 | [7 empty] | Carry out other design acitivities
Review / sign off other design activities | 5d | 2022-07-25 | 2022-07-29 | 42 | [6 empty] | Review / sign off other design activities
Research (Chetwood, Market and Behavioural) | 65d | 2022-06-13 | 2022-09-09 |  |  | TRUE |  |  |  |  | Research (Chetwood, Market and Behavioural) | IOOP Business | 3 |  | Activity Red |  | Left
Conduct Chetwoork research) | 60d | 2022-06-13 | 2022-09-02 | [7 empty] | Conduct Chetwoork research)
Review / sign off requirements from Chetwood research | 5d | 2022-09-05 | 2022-09-09 | 45 | [6 empty] | Review / sign off requirements from Chetwood research
High level business requirements baselined | 0 | 2022-06-24 | 2022-06-24 |  |  | TRUE |  |  |  |  | High level business requirements baselined | IOOP Business | 1 |  | Milestone Blue |  | Right
v1 Detailed business requirements baselined | 0 | 2022-07-29 | 2022-07-29 | 41 |  | TRUE |  |  |  |  | v1 Detailed business requirements baselined | IOOP Business | 2 |  | Milestone Blue |  | Right
v2 Detailed business requirements baselined | 0 | 2022-09-09 | 2022-09-09 | 44 |  | TRUE |  |  |  |  | v2 Detailed business requirements baselined | IOOP Business | 3 |  | Milestone Blue |  | Right
Business Implementation (training/comms etc) | 60d | 2022-11-14 | 2023-02-03 | 84FF |  | TRUE |  |  |  |  | Business Implementation (training/comms etc) | IOOP Business | 3 |  | Activity Green |  | Left
IOOP Technology | 120d | 2022-07-01 | 2022-12-15 | [7 empty] | IOOP Technology | IOOP Technology |  |  | Activity Green |  | Left
IT Core System Changes | 81d | 2022-07-22 | 2022-11-11 | [7 empty] | IT Core System Changes | IOOP Technology | 1 |  | Activity Green |  | Left
Define requirements for new set of terms | 10d | 2022-08-01 | 2022-08-12 |  |  | TRUE |  |  |  |  | Define requirements for new set of terms | IOOP Technology | 2 |  | Activity Green |  | Left
Get definition of changes to Charge File from Welcom | 0 | 2022-07-22 | 2022-07-22 | 68 |  | TRUE |  |  |  |  | Get definition of changes to Charge File from Welcom | IOOP Technology | 1 |  | Milestone Blue |  | Left
Define other requirements (RTI, charge file, statements/credit, other) | 30d | 2022-08-08 | 2022-09-16 |  |  | TRUE |  |  |  |  | Define other requirements (RTI, charge file, statements/credit, other) | IOOP Technology | 3 |  | Activity Green |  | Left
Define requirements to drive changes to charge file | 30d | 2022-08-08 | 2022-09-16 | 44FF +5d | [6 empty] | Define requirements to drive changes to charge file | IOOP Technology |  |  | Activity Red |  | Left
Define requirements to drive RTI changes | 30d | 2022-08-08 | 2022-09-16 | 44FF +5d | [6 empty] | Define requirements to drive RTI changes | IOOP Technology |  |  | Activity Green |  | Left
Define requirements to drive statements and credit agreement changes | 30d | 2022-08-08 | 2022-09-16 | 44FF +5d | [6 empty] | Define requirements to drive statements and credit agreement changes | IOOP Technology |  |  | Activity Green |  | Left
Define other requirements | 30d | 2022-08-08 | 2022-09-16 | 44FF +5d | [6 empty] | Define other requirements | IOOP Technology |  |  | Activity Green |  | Left
IT Core system changes (new set of terms) | 20d | 2022-08-15 | 2022-09-09 | 53 |  | TRUE |  |  |  |  | IT Core system changes (new set of terms) | IOOP Technology | 2 |  | Activity Green |  | Right
IT Core system changes (other) | 40d | 2022-09-19 | 2022-11-11 | 55 |  | TRUE |  |  |  |  | IT Core system changes (other) | IOOP Technology | 3 |  | Activity Red |  | Right
Digital Changes | 45d | 2022-09-12 | 2022-11-11 | [7 empty] | Digital Changes | IOOP Technology |  |  | Activity Green |  | Left
Carry out digital changes | 45d | 2022-09-12 | 2022-11-11 | 52FF |  | TRUE |  |  |  |  | Carry out digital changes | IOOP Technology | 4 |  | Activity Green |  | Left
Welcom | 120d | 2022-07-01 | 2022-12-15 | [7 empty] | Welcom | Welcom | 1 |  | Activity Green |  | Left
Receive scoping document (high level requirements + ownership) | 0 | 2022-07-01 | 2022-07-01 | 47FS +5d |  | TRUE |  |  |  |  | Receive scoping document (high level requirements + ownership) | Welcom | 1 |  | Milestone Blue |  | Left
Issue draft RFC | 0 | 2022-07-08 | 2022-07-08 | 65FS +5d |  | TRUE |  |  |  |  | Issue draft RFC | Welcom | 2 |  | Milestone Blue |  | Left
Sign off RFC | 0 | 2022-07-15 | 2022-07-15 | 66FS +5d |  | TRUE |  |  |  |  | Sign off RFC | Welcom | 2 |  | Milestone Blue |  | Right
Provide spec for changes to Charge File (TBD) | 0 | 2022-07-22 | 2022-07-22 | 67FS +5d |  | TRUE |  |  |  |  | Provide spec for changes to Charge File (TBD) | Welcom | 1 |  | Milestone Blue |  | Right
Carry out changes to Management Centre | 20d | 2022-09-14 | 2022-10-11 | 33 |  | TRUE |  |  |  |  | Carry out changes to Management Centre | Welcom | 3 |  | Activity Green |  | Left
Consultancy Support | 30d | 2022-07-15 | 2022-08-25 | 67 |  | TRUE |  |  |  |  | Consultancy Support | Welcom | 4 |  | Activity Green |  | Left
Environment and testing support | 80d | 2022-08-26 | 2022-12-15 | 70 |  | TRUE |  |  |  |  | Environment and testing support | Welcom | 4 |  | Activity Green |  | Left
Environments | 110d | 2022-06-27 | 2022-11-25 | [7 empty] | Environments | IOOP Environments |  |  | Activity Green |  | Left
Build PERF environment | 30d | 2022-06-27 | 2022-08-05 | 16 | PERF | TRUE |  |  |  |  | Build PERF environment | IOOP Environments | 1 |  | Activity Green |  | Left
Prep PERF for IOOP testing | 5d | 2022-11-07 | 2022-11-11 | 79SF |  | TRUE |  |  |  |  | Prep PERF for IOOP testing | IOOP Environments | 1 |  | Activity Green |  | Left
Prep MGMT environment | 10d | 2022-10-31 | 2022-11-11 | 81SF | MGMT | TRUE |  |  |  |  | Prep MGMT environment | IOOP Environments | 2 |  | Activity Green |  | Left
Prep ACPT environment | 10d | 2022-11-14 | 2022-11-25 | 80SF | ACPT | TRUE |  |  |  |  | Prep ACPT environment | IOOP Environments | 2 |  | Activity Green |  | Right
Build TRNG environment | [10 empty] | Build TRNG environment
Testing | 50d | 2022-11-14 | 2023-01-20 | [7 empty] | Testing | IOOP Testing / Implementation |  |  | Activity Green |  | Left
PERF Regression Testing | 10d | 2022-11-14 | 2022-11-25 | 60, 61, 63 |  | TRUE |  |  |  |  | PERF Regression Testing | IOOP Testing / Implementation | 2 |  | Activity Green |  | Left
ACPT Acquisition and Order Auth UAT | 10d | 2022-11-28 | 2022-12-09 | 79 |  | TRUE |  |  |  |  | ACPT Acquisition and Order Auth UAT | IOOP Testing / Implementation | 3 |  | Activity Green |  | Left
Business UAT (MGMT) | 50d | 2022-11-14 | 2023-01-20 | 60, 61, 63 |  | TRUE |  |  |  |  | Business UAT (MGMT) | IOOP Testing / Implementation | 1 |  | Activity Red |  | Left
Implementation | 30d | 2023-01-23 | 2023-03-03 | [7 empty] | Implementation | IOOP Testing / Implementation |  |  | Activity Green |  | Left
Go Live Readiness | 10d | 2023-01-23 | 2023-02-03 | 81 |  | TRUE |  |  |  |  | Go Live Readiness | IOOP Testing / Implementation | 2 |  | Activity Red |  | Left
Go Live (without Genesis impact) | 0 | 2023-02-03 | 2023-02-03 | 83 |  | TRUE |  |  |  |  | Go Live (without Genesis impact) | IOOP Testing / Implementation | 3 |  | Milestone Blue |  | Left
Estimated Genesis Impact | 20d | 2023-02-06 | 2023-03-03 | 84 |  | TRUE |  |  |  |  | Estimated Genesis Impact | IOOP Testing / Implementation | 1 | 3 | Genesis Impact
Go Live (with Genesis impact) | 0 | 2023-03-03 | 2023-03-03 | 85 |  | TRUE |  |  |  |  | Go Live (with Genesis impact) | IOOP Testing / Implementation | 3 |  | Milestone Red |  | Right