## Task_Table1
ID | Unique_ID | Outline_Level | Name | Start_Date | Finish_Date | Duration | Visual_Flag | Visual_Text | Swimlane | Track_Number | Num_Tracks | Format | Format_(Dummy) | Text_Layout
1 | 1 | 1 | Governance | 24 October 2022 08:00 | 13 January 2023 17:00 | 60 days | No |  | Governance |  | 0
2 | 2 | 2 | FSOC Dates | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | No |  | Governance |  | 0
3 | 3 | 3 | October FSOC | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | No |  | Governance | 1 | 0
4 | 4 | 3 | November FSOC | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | No |  | Governance | 1 | 0
5 | 5 | 3 | December FSOC | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | No |  | Governance | 1 | 0
6 | 6 | 2 | Sprints | 24 October 2022 08:00 | 13 January 2023 17:00 | 60 days | No |  | Sprints |  | 0
7 | 7 | 3 | Sprint 12 | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | Yes |  | Sprints | 2 | 0
8 | 8 | 3 | Sprint 13 | 21 November 2022 08:00 | 16 December 2022 17:00 | 20 days | Yes |  | Sprints | 2 | 0
9 | 9 | 3 | Sprint 14 | 19 December 2022 08:00 | 13 January 2023 17:00 | 20 days | Yes |  | Sprints | 2 | 0
10 | 10 | 1 | Discovery | 24 October 2022 08:00 | 27 January 2023 17:00 | 70 days | No |  |  |  | 0
11 | 11 | 2 | Sprint 12 Activities | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  |  |  | 0
12 | 12 | 3 | Get approval for New Customers solution approach | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
13 | 13 | 4 | Gain approval for Option 3 for New Customers | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
14 | 14 | 4 | Make decision on whether Appro will be required for IOOP. | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
15 | 15 | 3 | Get approval for Existing Customers implications | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
16 | 16 | 4 | Confirm options for Existing Customers (in advance of solution) | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
17 | 17 | 4 | Agree implications for Existing Customers | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
18 | 18 | 3 | Finalise commercials with Welcom and begin engagement | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
19 | 19 | 4 | Receive and sign off SOW from Welcom | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | IT |  | 0
20 | 20 | 4 | Complete data field analysis | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
21 | 21 | 4 | Engage with Welcom to discuss critical gaps in data mapping. | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
22 | 22 | 3 | Complete key business activities including research, legal impact analysis, consumer duty impact analysis | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Business | 2 | 0
23 | 23 | 4 | Complete Chetwood research (both qualitative and quantitative) | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Business |  | 0
24 | 24 | 4 | Consumer Duty - Complete initial impact assessment from CD requirements and New FS (Tanya/John C) | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Business |  | 0
25 | 25 | 4 | Complete legal impact analysis upon key product assets - specifically credit agreement | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Business |  | 0
26 | 26 | 4 | Update IOOP Bible with response to questions to Welcom once received. | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Business |  | 0
27 | 27 | 3 | Complete first iteration of UX design for checkout, application and direct debit (separate items) | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Cross Functional |  | 0
28 | 28 | 2 | Sprint 13 Activities | 21 November 2022 08:00 | 16 December 2022 17:00 | 20 days | No |  | Cross Functional | 4 | 0
29 | 29 | 2 | Deliverables | 24 October 2022 08:00 | 27 January 2023 17:00 | 70 days | No |  |  |  | 0
30 | 30 | 3 | Welcom Discovery Complete (Dates Speculative) | 24 October 2022 08:00 | 11 November 2022 17:00 | 15 days | No |  | Discovery Deliverables |  | 0
31 | 31 | 4 | Welcom SOW Sign Off | 24 October 2022 08:00 | 28 October 2022 17:00 | 5 days | No |  | Discovery Deliverables |  | 0
32 | 32 | 4 | Welcom Discovery | 31 October 2022 08:00 | 11 November 2022 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
33 | 33 | 4 | Welcom Discovery Complete | 11 November 2022 17:00 | 11 November 2022 17:00 | 0 days | No |  | Discovery Deliverables |  | 0
34 | 34 | 3 | Signed Off Requirements | 24 October 2022 08:00 | 11 November 2022 17:00 | 15 days | No |  | Discovery Deliverables |  | 0
35 | 35 | 4 | Issue updated BRD after latest feedback (CD analysis and review comments) | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | No |  | Discovery Deliverables |  | 0
36 | 36 | 4 | BRD Review/sign off | 24 October 2022 08:00 | 11 November 2022 17:00 | 15 days | No |  | Discovery Deliverables |  | 0
37 | 37 | 4 | BRD Signed Off | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | No |  | Discovery Deliverables |  | 0
38 | 38 | 3 | Solution Definition/Overview Doc | 24 October 2022 08:00 | 18 November 2022 17:00 | 20 days | No |  | Discovery Deliverables |  | 0
39 | 39 | 4 | Write Solution Definition | 24 October 2022 08:00 | 11 November 2022 17:00 | 15 days | Yes |  | Discovery Deliverables |  | 0
40 | 40 | 4 | Solution Definition Review/sign off | 14 November 2022 08:00 | 18 November 2022 17:00 | 5 days | Yes |  | Discovery Deliverables |  | 0
41 | 41 | 4 | Solution Design Signed Off | 18 November 2022 17:00 | 18 November 2022 17:00 | 0 days | Yes |  | Discovery Deliverables |  | 0
42 | 42 | 3 | E2E Impact Assessment | 19 December 2022 08:00 | 27 January 2023 17:00 | 30 days | No |  | Discovery Deliverables |  | 0
43 | 43 | 4 | Write E2E Impact Assessment | 19 December 2022 08:00 | 30 December 2022 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
44 | 44 | 4 | E2E Impact Assessment Review/sign off | 02 January 2023 08:00 | 13 January 2023 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
45 | 45 | 4 | E2E Impact Assessment Signed Off | 16 January 2023 08:00 | 27 January 2023 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
46 | 46 | 3 | Non Functional Requirements | 14 November 2022 08:00 | 02 December 2022 17:00 | 15 days | No |  | Discovery Deliverables |  | 0
47 | 47 | 4 | Write NFRs | 14 November 2022 08:00 | 25 November 2022 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
48 | 48 | 4 | NFRs Review/sign off | 28 November 2022 08:00 | 02 December 2022 17:00 | 5 days | No |  | Discovery Deliverables |  | 0
49 | 49 | 4 | NFRs Signed Off | 02 December 2022 17:00 | 02 December 2022 17:00 | 0 days | No |  | Discovery Deliverables |  | 0
50 | 50 | 3 | Implementation & Cutover Strategy/Recommendation | 14 November 2022 08:00 | 02 December 2022 17:00 | 15 days | No |  | Discovery Deliverables |  | 0
51 | 51 | 4 | Write Implementation & Cutover Strategy/Recommendation | 14 November 2022 08:00 | 25 November 2022 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
52 | 52 | 4 | Implementation & Cutover Strategy/Recommendation Review/sign off | 28 November 2022 08:00 | 02 December 2022 17:00 | 5 days | No |  | Discovery Deliverables |  | 0
53 | 53 | 4 | Implementation & Cutover Strategy/Recommendation Signed Off | 02 December 2022 17:00 | 02 December 2022 17:00 | 0 days | No |  | Discovery Deliverables |  | 0
54 | 54 | 3 | Delivery Plan | 14 November 2022 08:00 | 02 December 2022 17:00 | 15 days | No |  | Discovery Deliverables |  | 0
55 | 55 | 4 | Write Delivery Plan | 14 November 2022 08:00 | 25 November 2022 17:00 | 10 days | No |  | Discovery Deliverables |  | 0
56 | 56 | 4 | Delivery Plan Review/sign off | 28 November 2022 08:00 | 02 December 2022 17:00 | 5 days | No |  | Discovery Deliverables |  | 0
57 | 57 | 4 | Delivery Plan Signed Off | 02 December 2022 17:00 | 02 December 2022 17:00 | 0 days | No |  | Discovery Deliverables |  | 0
58 | 58 | 3 | Target End Of Discovery | 24 October 2022 08:00 | 24 October 2022 08:00 | 0 days | Yes |  | Discovery Deliverables |  | 0