## Task_Table1
Outline_Level | Outline_Number | Name | Duration | Start_Date | Finish_Date | ID | Milestone
1 | 1 | FGH Transformation Plan | 517 days? | 06 June 2022 08:00 | 28 May 2024 17:00 | 1 | No
2 | 1.1 | Transformation Kickoff | 1 day | 06 June 2022 08:00 | 06 June 2022 17:00 | 2 | No
2 | 1.2 | Required Environments and Strategy Review | 1 day | 06 June 2022 08:00 | 06 June 2022 17:00 | 3 | No
2 | 1.3 | Project - on hold | 85 days | 07 June 2022 08:00 | 03 October 2022 17:00 | 4 | No
2 | 1.4 | Environments Stragegy and Setup Sign Off | 20 days | 15 May 2023 08:00 | 09 June 2023 17:00 | 5 | No
3 | 1.4.1 | Environment Setup | 20 days | 15 May 2023 08:00 | 09 June 2023 17:00 | 6 | No
2 | 1.5 | Product Capability Mapping | 12 days | 04 October 2022 08:00 | 19 October 2022 17:00 | 7 | No
3 | 1.5.1 | Marketing | 1 day | 04 October 2022 08:00 | 04 October 2022 17:00 | 8 | No
3 | 1.5.2 | Customer Service | 1 day | 05 October 2022 08:00 | 05 October 2022 17:00 | 9 | No
3 | 1.5.3 | Customer Service Product Demo | 1 day | 17 October 2022 08:00 | 17 October 2022 17:00 | 10 | No
3 | 1.5.4 | Financial Service | 1 day | 19 October 2022 08:00 | 19 October 2022 17:00 | 11 | No
2 | 1.6 | Customer Service workshop plan | 9 days | 20 October 2022 08:00 | 01 November 2022 17:00 | 12 | No
2 | 1.7 | Marketing Workshop plan | 5 days | 07 November 2022 08:00 | 11 November 2022 17:00 | 13 | No
2 | 1.8 | FastTrack Engagement | 126 days? | 05 June 2023 08:00 | 27 November 2023 17:00 | 14 | No
3 | 1.8.1 | Kick off meeting | 1 day | 05 June 2023 08:00 | 05 June 2023 17:00 | 15 | No
3 | 1.8.2 | Project Scope PPT | 1 day | 19 June 2023 08:00 | 19 June 2023 17:00 | 16 | No
3 | 1.8.3 | Documentation Preparation | 70 days | 07 August 2023 08:00 | 10 November 2023 17:00 | 17 | No
3 | 1.8.4 | Documentation Review | 10 days | 13 November 2023 08:00 | 24 November 2023 17:00 | 18 | No
3 | 1.8.5 | Sign off | 1 day? | 27 November 2023 08:00 | 27 November 2023 17:00 | 19 | No
2 | 1.9 | Dependencies | 86 days | 01 September 2023 08:00 | 29 December 2023 17:00 | 20 | No
3 | 1.9.1 | Nice in Contact | 86 days | 01 September 2023 08:00 | 29 December 2023 17:00 | 21 | No
3 | 1.9.2 | Finalization of Queues | 9 days | 10 October 2023 08:00 | 20 October 2023 17:00 | 22 | No
3 | 1.9.3 | SMS Bulk Upload & real time | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 23 | No
3 | 1.9.4 | Financier Application Integration | 60 days | 01 September 2023 08:00 | 23 November 2023 17:00 | 24 | No
3 | 1.9.5 | Document Storage | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 25 | No
3 | 1.9.6 | Webform Creation | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 26 | No
3 | 1.9.7 | Customer Data Model | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 27 | No
3 | 1.9.8 | Integration with Adobe Campaign | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 28 | No
3 | 1.9.9 | Integration with Medellia | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 29 | No
3 | 1.9.10 | Call Center - Order Management | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 30 | No
3 | 1.9.11 | Apollo Campaign | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 31 | No
3 | 1.9.12 | Test Strategy - Program Level | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 32 | No
3 | 1.9.13 | Cut over Strategy | 40 days | 01 September 2023 08:00 | 26 October 2023 17:00 | 33 | No
2 | 1.10 | Discover Sessions | 239 days? | 17 October 2022 08:00 | 14 September 2023 17:00 | 34 | No
3 | 1.10.1 | Customer Service Discover Sessions | 131 days? | 02 November 2022 08:00 | 03 May 2023 17:00 | 35 | No
4 | 1.10.1.1 | Communicate with customers - Email Communciations | 5 days | 02 November 2022 08:00 | 08 November 2022 17:00 | 36 | No
4 | 1.10.1.2 | Communicate with customers - Phone | 4 days | 09 November 2022 08:00 | 14 November 2022 17:00 | 37 | No
4 | 1.10.1.3 | Communicate with customers - SMS,Website.Webchat,Social Media & Paper Mail) | 1 day | 15 November 2022 08:00 | 15 November 2022 17:00 | 38 | No
4 | 1.10.1.4 | Customer management - Create & Update Customer | 1 day | 16 November 2022 08:00 | 16 November 2022 17:00 | 39 | No
4 | 1.10.1.5 | Complaint Management | 6 days | 17 November 2022 08:00 | 24 November 2022 17:00 | 40 | No
4 | 1.10.1.6 | Order fulfilment - Create , Update , Delete , Addition | 2 days | 28 November 2022 08:00 | 29 November 2022 17:00 | 41 | No
4 | 1.10.1.7 | Reports & Dashboards | 1 day | 28 November 2022 08:00 | 28 November 2022 17:00 | 42 | No
4 | 1.10.1.8 | Documentation of BRD | 10 days | 29 November 2022 08:00 | 12 December 2022 17:00 | 43 | No
4 | 1.10.1.9 | BRD Review | 10 days | 13 December 2022 08:00 | 26 December 2022 17:00 | 44 | No
4 | 1.10.1.10 | BRD Feedback Update | 2 days | 27 December 2022 08:00 | 28 December 2022 17:00 | 45 | No
4 | 1.10.1.11 | Documentation of Fit Gap Document | 1 day | 27 December 2022 08:00 | 27 December 2022 17:00 | 46 | No
4 | 1.10.1.12 | Discovery Session on Mainframes | 1 day? | 23 February 2023 08:00 | 23 February 2023 17:00 | 47 | No
4 | 1.10.1.13 | BRD Sign Off | 1 day | 03 May 2023 08:00 | 03 May 2023 17:00 | 48 | No
3 | 1.10.2 | Customer Service Milestone Deliverables | 195 days? | 17 October 2022 08:00 | 14 July 2023 17:00 | 49 | No
4 | 1.10.2.1 | As-is understanding document / BRD :- Application demos1 | 1 day? | 17 October 2022 08:00 | 17 October 2022 17:00 | 50 | No
4 | 1.10.2.2 | As-is understanding document / BRD :- As-is FGH business processes | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 51 | No
4 | 1.10.2.3 | Requirements register :- Business process and requirements | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 52 | No
4 | 1.10.2.4 | Requirements register :- FIT / GAP analysis | 1 day | 07 June 2023 08:00 | 07 June 2023 17:00 | 53 | No
4 | 1.10.2.5 | Requirements register :- MOSCOW prioritization of requirements | 1 day | 19 May 2023 08:00 | 19 May 2023 17:00 | 54 | No
4 | 1.10.2.6 | Plan :- Full plan including UAT/Go-live | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 55 | No
4 | 1.10.2.7 | As-is architecture :- As-Is Process Catalog | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 56 | No
4 | 1.10.2.8 | As-is architecture :- As-Is Application Catalog | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 57 | No
4 | 1.10.2.9 | As-is architecture :- -As-Is Application-Process Mapping | 27 days | 08 June 2023 08:00 | 14 July 2023 17:00 | 58 | No
4 | 1.10.2.10 | As-is architecture :- -As-Is Interface Catalog | 2 days | 08 June 2023 08:00 | 09 June 2023 17:00 | 59 | No
4 | 1.10.2.11 | As-is architecture :- -As-Is Data Catalog | 2 days | 08 June 2023 08:00 | 09 June 2023 17:00 | 60 | No
4 | 1.10.2.12 | As-is architecture :- -As-Is Overview Deck | 27 days | 08 June 2023 08:00 | 14 July 2023 17:00 | 61 | No
4 | 1.10.2.13 | To-be Solution Architecture (what/not how) :- Solution overiew Deck | 27 days | 08 June 2023 08:00 | 14 July 2023 17:00 | 62 | No
4 | 1.10.2.14 | To-be Solution Architecture (what/not how) :- -Solution Outline Doc | 39 days | 23 May 2023 08:00 | 14 July 2023 17:00 | 63 | No
4 | 1.10.2.15 | Enterprise Architecture (what)/not how at this stage) :- -EA Model, Catalogs & Maps | 0 days | 07 June 2023 17:00 | 07 June 2023 17:00 | 64 | Yes
4 | 1.10.2.16 | Enterprise Architecture (what)/not how at this stage) :- Transition State Architecture | 0 days | 22 June 2023 17:00 | 22 June 2023 17:00 | 65 | Yes
4 | 1.10.2.17 | Requirements register :- Show & Tell sessions | 6 days | 26 June 2023 08:00 | 03 July 2023 17:00 | 66 | No
3 | 1.10.3 | Marketing Discover Sessions | 137 days | 07 December 2022 08:00 | 15 June 2023 17:00 | 67 | No
4 | 1.10.3.1 | AS - IS Study & Kick off Session | 2 days | 07 December 2022 08:00 | 08 December 2022 17:00 | 68 | No
4 | 1.10.3.2 | Campaign Identification - Day 1 | 1 day | 15 December 2022 08:00 | 15 December 2022 17:00 | 69 | No
4 | 1.10.3.3 | Content creation - Day 1 | 1 day | 16 December 2022 08:00 | 16 December 2022 17:00 | 70 | No
4 | 1.10.3.4 | Content creation - Day 2 | 1 day | 21 December 2022 08:00 | 21 December 2022 17:00 | 71 | No
4 | 1.10.3.5 | Campaign Identification - Day 2 | 1 day | 04 January 2023 08:00 | 04 January 2023 17:00 | 72 | No
4 | 1.10.3.6 | Campaign Design & Planning | 2 days | 05 January 2023 08:00 | 06 January 2023 17:00 | 73 | No
4 | 1.10.3.7 | Campaign Design & Planning | 1 day | 10 January 2023 08:00 | 10 January 2023 17:00 | 74 | No
4 | 1.10.3.8 | Promotional activities | 2 days | 10 January 2023 08:00 | 11 January 2023 17:00 | 75 | No
4 | 1.10.3.9 | Brand representation | 1 day | 12 January 2023 08:00 | 12 January 2023 17:00 | 76 | No
4 | 1.10.3.10 | Campaign Execution | 2 days | 11 January 2023 08:00 | 12 January 2023 17:00 | 77 | No
4 | 1.10.3.11 | Customer Loyality | 1 day | 19 January 2023 08:00 | 19 January 2023 17:00 | 78 | No
4 | 1.10.3.12 | Campaign Analysis | 1 day | 13 January 2023 08:00 | 13 January 2023 17:00 | 79 | No
4 | 1.10.3.13 | Campaign Analysis - Day 2 | 1 day | 17 January 2023 08:00 | 17 January 2023 17:00 | 80 | No
4 | 1.10.3.14 | Reports & Dashboards | 1 day | 17 January 2023 08:00 | 17 January 2023 17:00 | 81 | No
4 | 1.10.3.15 | Customer Forecast & planning | 1 day | 18 January 2023 08:00 | 18 January 2023 17:00 | 82 | No
4 | 1.10.3.16 | Tracking customer sentiment | 1 day | 18 January 2023 08:00 | 18 January 2023 17:00 | 83 | No
4 | 1.10.3.17 | Pimberly | 1 day | 19 January 2023 08:00 | 19 January 2023 17:00 | 84 | No
4 | 1.10.3.18 | Organization Chart and Security Matrix | 1 day | 19 January 2023 08:00 | 19 January 2023 17:00 | 85 | No
4 | 1.10.3.19 | Teradata | 1 day | 20 January 2023 08:00 | 20 January 2023 17:00 | 86 | No
4 | 1.10.3.20 | Affiliate Marketing | 1 day | 01 February 2023 08:00 | 01 February 2023 17:00 | 87 | No
4 | 1.10.3.21 | Apollo Process | 1 day | 03 February 2023 08:00 | 03 February 2023 17:00 | 88 | No
4 | 1.10.3.22 | Catalogue Printing | 1 day | 14 February 2023 08:00 | 14 February 2023 17:00 | 89 | No
4 | 1.10.3.23 | Documentation of BRD | 10 days | 15 February 2023 08:00 | 28 February 2023 17:00 | 90 | No
4 | 1.10.3.24 | Documentation of Fit Gap Document | 1 day | 15 February 2023 08:00 | 15 February 2023 17:00 | 91 | No
4 | 1.10.3.25 | Internal BRD1 Review | 10 days | 06 March 2023 08:00 | 17 March 2023 17:00 | 92 | No
4 | 1.10.3.26 | Internal BRD2 Review | 10 days | 21 March 2023 08:00 | 03 April 2023 17:00 | 93 | No
4 | 1.10.3.27 | Internal BRD1 Sign off | 1 day | 20 March 2023 08:00 | 20 March 2023 17:00 | 94 | No
4 | 1.10.3.28 | Internal BRD2 Sign off | 1 day | 04 April 2023 08:00 | 04 April 2023 17:00 | 95 | No
4 | 1.10.3.29 | Missing Application Workshop | 1 day | 12 May 2023 08:00 | 12 May 2023 17:00 | 96 | No
4 | 1.10.3.30 | Documentation of BRD | 3 days | 15 May 2023 08:00 | 17 May 2023 17:00 | 97 | No
4 | 1.10.3.31 | Internal Review | 3 days | 18 May 2023 08:00 | 22 May 2023 17:00 | 98 | No
4 | 1.10.3.32 | Business BRD Review | 10 days | 01 June 2023 08:00 | 14 June 2023 17:00 | 99 | No
4 | 1.10.3.33 | Sign Off | 1 day | 15 June 2023 08:00 | 15 June 2023 17:00 | 100 | No
3 | 1.10.4 | Marketing Milestone Deliverables | 202 days? | 07 December 2022 08:00 | 14 September 2023 17:00 | 101 | No
4 | 1.10.4.1 | As-is understanding document / BRD :- Application demos1 | 1 day? | 07 December 2022 08:00 | 07 December 2022 17:00 | 102 | No
4 | 1.10.4.2 | As-is understanding document / BRD :- As-is FGH business processes | 1 day? | 15 June 2023 08:00 | 15 June 2023 17:00 | 103 | No
4 | 1.10.4.3 | Requirements register :- Business process and requirements | 1 day? | 15 June 2023 08:00 | 15 June 2023 17:00 | 104 | No
4 | 1.10.4.4 | Requirements register :- FIT / GAP analysis | 60 days | 16 June 2023 08:00 | 07 September 2023 17:00 | 105 | No
4 | 1.10.4.5 | Requirements register :- MOSCOW prioritization of requirements | 10 days | 17 July 2023 08:00 | 28 July 2023 17:00 | 106 | No
4 | 1.10.4.6 | Plan :- Full plan including UAT/Go-live | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 107 | No
4 | 1.10.4.7 | As-is architecture :- As-Is Process Catalog | 1 day? | 15 June 2023 08:00 | 15 June 2023 17:00 | 108 | No
4 | 1.10.4.8 | As-is architecture :- As-Is Application Catalog | 1 day? | 15 June 2023 08:00 | 15 June 2023 17:00 | 109 | No
4 | 1.10.4.9 | As-is architecture :- -As-Is Application-Process Mapping | 2 days | 07 August 2023 08:00 | 08 August 2023 17:00 | 110 | No
4 | 1.10.4.10 | As-is architecture :- -As-Is Interface Catalog | 11 days | 07 August 2023 08:00 | 21 August 2023 17:00 | 111 | No
4 | 1.10.4.11 | As-is architecture :- -As-Is Data Catalog | 5 days | 01 September 2023 08:00 | 07 September 2023 17:00 | 112 | No
4 | 1.10.4.12 | As-is architecture :- -As-Is Overview Deck | 11 days | 07 August 2023 08:00 | 21 August 2023 17:00 | 113 | No
4 | 1.10.4.13 | To-be Solution Architecture (what/not how) :- Solution overiew Deck | 11 days | 07 August 2023 08:00 | 21 August 2023 17:00 | 114 | No
4 | 1.10.4.14 | To-be Solution Architecture (what/not how) :- -Solution Outline Doc | 10 days | 01 September 2023 08:00 | 14 September 2023 17:00 | 115 | No
3 | 1.10.5 | Financial Services Discover Sessions | 72 days? | 22 February 2023 08:00 | 01 June 2023 17:00 | 116 | No
4 | 1.10.5.1 | Regulated Compliants | 1 day | 22 February 2023 08:00 | 22 February 2023 17:00 | 117 | No
4 | 1.10.5.2 | Fraud & Credit Operations | 1 day | 24 February 2023 08:00 | 24 February 2023 17:00 | 118 | No
4 | 1.10.5.3 | Internal Review of MoMs | 1 day | 06 March 2023 08:00 | 06 March 2023 17:00 | 119 | No
4 | 1.10.5.4 | Publish Of MoMs | 1 day | 09 March 2023 08:00 | 09 March 2023 17:00 | 120 | No
4 | 1.10.5.5 | Collections | 1 day | 15 March 2023 08:00 | 15 March 2023 17:00 | 121 | No
4 | 1.10.5.6 | Publish MoM for Internal Review | 1 day? | 20 March 2023 08:00 | 20 March 2023 17:00 | 122 | No
4 | 1.10.5.7 | Internal Review of Mom | 2 days | 21 March 2023 08:00 | 22 March 2023 17:00 | 123 | No
4 | 1.10.5.8 | Publish of MOM -- Collections | 2 days | 23 March 2023 08:00 | 24 March 2023 17:00 | 124 | No
4 | 1.10.5.9 | Documentation of BRD | 15 days | 27 March 2023 08:00 | 14 April 2023 17:00 | 125 | No
4 | 1.10.5.10 | Documentation of Fit Gap document | 1 day | 10 April 2023 08:00 | 10 April 2023 17:00 | 126 | No
4 | 1.10.5.11 | Internal BRD Review | 5 days | 01 May 2023 08:00 | 05 May 2023 17:00 | 127 | No
4 | 1.10.5.12 | Internal BRD Sign off | 1 day | 08 May 2023 08:00 | 08 May 2023 17:00 | 128 | No
4 | 1.10.5.13 | BRD Review | 18 days | 09 May 2023 08:00 | 01 June 2023 17:00 | 129 | No
4 | 1.10.5.14 | Sign Off | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00 | 130 | No
3 | 1.10.6 | Financial Services Milestone Deliverables | 193 days? | 19 October 2022 08:00 | 14 July 2023 17:00 | 131 | No
4 | 1.10.6.1 | As-is understanding document / BRD :- Application demos1 | 1 day? | 19 October 2022 08:00 | 19 October 2022 17:00 | 132 | No
4 | 1.10.6.2 | As-is understanding document / BRD :- As-is FGH business processes | 1 day? | 02 June 2023 08:00 | 02 June 2023 17:00 | 133 | No
4 | 1.10.6.3 | Requirements register :- Business process and requirements | 1 day? | 02 June 2023 08:00 | 02 June 2023 17:00 | 134 | No
4 | 1.10.6.4 | Requirements register :- FIT / GAP analysis | 1 day | 13 June 2023 08:00 | 13 June 2023 17:00 | 135 | No
4 | 1.10.6.5 | Requirements register :- MOSCOW prioritization of requirements | 1 day | 02 June 2023 08:00 | 02 June 2023 17:00 | 136 | No
4 | 1.10.6.6 | Plan :- Full plan including UAT/Go-live | 1 day? | 03 May 2023 08:00 | 03 May 2023 17:00 | 137 | No
4 | 1.10.6.7 | As-is architecture :- As-Is Process Catalog | 1 day? | 02 June 2023 08:00 | 02 June 2023 17:00 | 138 | No
4 | 1.10.6.8 | As-is architecture :- As-Is Application Catalog | 1 day? | 16 June 2023 08:00 | 16 June 2023 17:00 | 139 | No
4 | 1.10.6.9 | As-is architecture :- -As-Is Application-Process Mapping | 1 day | 23 June 2023 08:00 | 23 June 2023 17:00 | 140 | No
4 | 1.10.6.10 | As-is architecture :- -As-Is Interface Catalog | 1 day | 23 June 2023 08:00 | 23 June 2023 17:00 | 141 | No
4 | 1.10.6.11 | As-is architecture :- -As-Is Data Catalog | 16 days | 23 June 2023 08:00 | 14 July 2023 17:00 | 142 | No
4 | 1.10.6.12 | As-is architecture :- -As-Is Overview Deck | 16 days | 23 June 2023 08:00 | 14 July 2023 17:00 | 143 | No
4 | 1.10.6.13 | To-be Solution Architecture (what/not how) :- Solution overiew Deck | 16 days | 23 June 2023 08:00 | 14 July 2023 17:00 | 144 | No
4 | 1.10.6.14 | To-be Solution Architecture (what/not how) :- -Solution Outline Doc | 16 days | 23 June 2023 08:00 | 14 July 2023 17:00 | 145 | No
4 | 1.10.6.15 | Enterprise Architecture (what)/not how at this stage) :- -EA Model, Catalogs & Maps | 0 days | 23 June 2023 08:00 | 23 June 2023 08:00 | 146 | Yes
4 | 1.10.6.16 | Enterprise Architecture (what)/not how at this stage) :- Transition State Architecture | 0 days | 30 June 2023 08:00 | 30 June 2023 08:00 | 147 | Yes
4 | 1.10.6.17 | Requirements register :- Show & Tell sessions | 7 days | 23 June 2023 08:00 | 03 July 2023 17:00 | 148 | No
2 | 1.11 | Design and Configure | 162 days | 04 May 2023 08:00 | 15 December 2023 17:00 | 149 | No
3 | 1.11.1 | Customer Service | 74 days | 04 May 2023 08:00 | 15 August 2023 17:00 | 150 | No
4 | 1.11.1.1 | Document preparation of FDD | 14 days | 04 May 2023 08:00 | 23 May 2023 17:00 | 151 | No
4 | 1.11.1.2 | Finalization of Customer Service Architecture | 14 days | 04 May 2023 08:00 | 23 May 2023 17:00 | 152 | No
4 | 1.11.1.3 | Mockup Screen Building | 14 days | 04 May 2023 08:00 | 23 May 2023 17:00 | 153 | No
4 | 1.11.1.4 | FDD Review | 10 days | 24 May 2023 08:00 | 06 June 2023 17:00 | 154 | No
4 | 1.11.1.5 | FDD Review & Update | 30 days | 21 June 2023 08:00 | 01 August 2023 17:00 | 155 | No
4 | 1.11.1.6 | FDD Review Workshop with Users | 5 days | 02 August 2023 08:00 | 08 August 2023 17:00 | 156 | No
4 | 1.11.1.7 | Splitting of FDDs of CS & FS | 5 days | 09 August 2023 08:00 | 15 August 2023 17:00 | 157 | No
3 | 1.11.2 | Marketing | 56 days | 30 August 2023 08:00 | 15 November 2023 17:00 | 158 | No
4 | 1.11.2.1 | Document preparation of FDD | 45 days | 30 August 2023 08:00 | 31 October 2023 17:00 | 159 | No
4 | 1.11.2.2 | FDD Review | 5 days | 01 November 2023 08:00 | 07 November 2023 17:00 | 160 | No
4 | 1.11.2.3 | FDD Review Update | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 161 | No
4 | 1.11.2.4 | FDD final Review | 3 days | 10 November 2023 08:00 | 14 November 2023 17:00 | 162 | No
4 | 1.11.2.5 | FDD signoff | 1 day | 15 November 2023 08:00 | 15 November 2023 17:00 | 163 | No
3 | 1.11.3 | Financial Services | 53 days | 02 June 2023 08:00 | 15 August 2023 17:00 | 164 | No
4 | 1.11.3.1 | Document preparation of FDD | 10 days | 02 June 2023 08:00 | 15 June 2023 17:00 | 165 | No
4 | 1.11.3.2 | Finalization of Financial Services Architecture | 10 days | 02 June 2023 08:00 | 15 June 2023 17:00 | 166 | No
4 | 1.11.3.3 | Mockup Screen Building | 10 days | 02 June 2023 08:00 | 15 June 2023 17:00 | 167 | No
4 | 1.11.3.4 | FDD Review | 5 days | 23 June 2023 08:00 | 29 June 2023 17:00 | 168 | No
4 | 1.11.3.5 | FDD Review & Update | 30 days | 30 June 2023 08:00 | 10 August 2023 17:00 | 169 | No
4 | 1.11.3.6 | FDD Review Workshop with Users | 5 days | 02 August 2023 08:00 | 08 August 2023 17:00 | 170 | No
4 | 1.11.3.7 | Splitting of CS & FS FDDs | 5 days | 09 August 2023 08:00 | 15 August 2023 17:00 | 171 | No
3 | 1.11.4 | Common FDDs for CS & FS | 60 days | 16 August 2023 08:00 | 07 November 2023 17:00 | 172 | No
4 | 1.11.4.1 | Customer Search | 3 days | 16 August 2023 08:00 | 18 August 2023 17:00 | 173 | No
4 | 1.11.4.2 | Customer Search FDD Review | 5 days | 21 August 2023 08:00 | 25 August 2023 17:00 | 174 | No
4 | 1.11.4.3 | Customer Search FDD Review Updates | 2 days | 28 August 2023 08:00 | 29 August 2023 17:00 | 175 | No
4 | 1.11.4.4 | Customer Search Final Review | 22 days | 30 August 2023 08:00 | 28 September 2023 17:00 | 176 | No
4 | 1.11.4.5 | Customer Search Review Sign off | 1 day | 29 September 2023 08:00 | 29 September 2023 17:00 | 177 | No
4 | 1.11.4.6 | Knowledge Management | 4 days | 16 August 2023 08:00 | 21 August 2023 17:00 | 178 | No
4 | 1.11.4.7 | Knowledge Management FDD Review | 5 days | 22 August 2023 08:00 | 28 August 2023 17:00 | 179 | No
4 | 1.11.4.8 | Knowledge Management FDD Review Updates | 2 days | 29 August 2023 08:00 | 30 August 2023 17:00 | 180 | No
4 | 1.11.4.9 | Knowledge Management Final Review | 21 days | 31 August 2023 08:00 | 28 September 2023 17:00 | 181 | No
4 | 1.11.4.10 | Knowledge Management Review Sign off | 1 day | 29 September 2023 08:00 | 29 September 2023 17:00 | 182 | No
4 | 1.11.4.11 | Enquiry Management | 28 days | 22 August 2023 08:00 | 28 September 2023 17:00 | 183 | No
4 | 1.11.4.12 | Enquiry Management FDD Review | 1 day | 29 September 2023 08:00 | 29 September 2023 17:00 | 184 | No
4 | 1.11.4.13 | Enquiry Management FDD Review Updates | 6 days | 02 October 2023 08:00 | 09 October 2023 17:00 | 185 | No
4 | 1.11.4.14 | Enquiry Management Final Review | 8 days | 10 October 2023 08:00 | 19 October 2023 17:00 | 186 | No
4 | 1.11.4.15 | Enquiry Management Review Sign off | 1 day | 20 October 2023 08:00 | 20 October 2023 17:00 | 187 | No
4 | 1.11.4.16 | Regulated Complaint Management | 39 days | 22 August 2023 08:00 | 13 October 2023 17:00 | 188 | No
4 | 1.11.4.17 | Regulated Complaint Managemen FDD Review | 5 days | 16 October 2023 08:00 | 20 October 2023 17:00 | 189 | No
4 | 1.11.4.18 | Regulated Complaint Managemen FDD Review Updates | 3 days | 23 October 2023 08:00 | 25 October 2023 17:00 | 190 | No
4 | 1.11.4.19 | Regulated Complaint Managemen Final Review | 5 days | 26 October 2023 08:00 | 01 November 2023 17:00 | 191 | No
4 | 1.11.4.20 | Regulated Complaint Managemen Review Sign off | 1 day | 02 November 2023 08:00 | 02 November 2023 17:00 | 192 | No
4 | 1.11.4.21 | Non- regulated Complaint Management | 41 days | 22 August 2023 08:00 | 17 October 2023 17:00 | 193 | No
4 | 1.11.4.22 | Non- regulated Complaint Management FDD Review | 5 days | 18 October 2023 08:00 | 24 October 2023 17:00 | 194 | No
4 | 1.11.4.23 | Non- regulated Complaint Management FDD Review Updates | 2 days | 25 October 2023 08:00 | 26 October 2023 17:00 | 195 | No
4 | 1.11.4.24 | Non- regulated Complaint Management Final Review | 5 days | 27 October 2023 08:00 | 02 November 2023 17:00 | 196 | No
4 | 1.11.4.25 | Non- regulated Complaint Management Review Sign off | 1 day | 03 November 2023 08:00 | 03 November 2023 17:00 | 197 | No
4 | 1.11.4.26 | Activity Management | 21 days | 28 August 2023 08:00 | 25 September 2023 17:00 | 198 | No
4 | 1.11.4.27 | Activity Management FDD Review | 8 days | 26 September 2023 08:00 | 05 October 2023 17:00 | 199 | No
4 | 1.11.4.28 | Activity Management FDD Review Updates | 2 days | 06 October 2023 08:00 | 09 October 2023 17:00 | 200 | No
4 | 1.11.4.29 | Activity Management Final Review | 8 days | 10 October 2023 08:00 | 19 October 2023 17:00 | 201 | No
4 | 1.11.4.30 | Activity Management Review Sign off | 1 day | 20 October 2023 08:00 | 20 October 2023 17:00 | 202 | No
4 | 1.11.4.31 | SLA Management | 21 days | 28 August 2023 08:00 | 25 September 2023 17:00 | 203 | No
4 | 1.11.4.32 | SLA Management FDD Review | 10 days | 26 September 2023 08:00 | 09 October 2023 17:00 | 204 | No
4 | 1.11.4.33 | SLA Management FDD Review Updates | 3 days | 10 October 2023 08:00 | 12 October 2023 17:00 | 205 | No
4 | 1.11.4.34 | SLA Management Final Review | 5 days | 13 October 2023 08:00 | 19 October 2023 17:00 | 206 | No
4 | 1.11.4.35 | SLA Management Review Sign off | 1 day | 20 October 2023 08:00 | 20 October 2023 17:00 | 207 | No
4 | 1.11.4.36 | Case Routing/Queue Management | 40 days | 28 August 2023 08:00 | 20 October 2023 17:00 | 208 | No
4 | 1.11.4.37 | Queue Management FDD Review | 5 days | 23 October 2023 08:00 | 27 October 2023 17:00 | 209 | No
4 | 1.11.4.38 | Queue Management FDD Review Updates | 2 days | 30 October 2023 08:00 | 31 October 2023 17:00 | 210 | No
4 | 1.11.4.39 | Queue Management Final Review | 4 days | 01 November 2023 08:00 | 06 November 2023 17:00 | 211 | No
4 | 1.11.4.40 | Queue Management Review Sign off | 1 day | 07 November 2023 08:00 | 07 November 2023 17:00 | 212 | No
3 | 1.11.5 | Common Design Milestone Documents | 109 days | 30 June 2023 08:00 | 29 November 2023 17:00 | 213 | No
4 | 1.11.5.1 | Solution Design Document | 10 days | 23 October 2023 08:00 | 03 November 2023 17:00 | 214 | No
4 | 1.11.5.2 | SDD Review with ARB | 5 days | 06 November 2023 08:00 | 10 November 2023 17:00 | 215 | No
4 | 1.11.5.3 | SDD Review Updates | 2 days | 13 November 2023 08:00 | 14 November 2023 17:00 | 216 | No
4 | 1.11.5.4 | SDD Final Review | 10 days | 15 November 2023 08:00 | 28 November 2023 17:00 | 217 | No
4 | 1.11.5.5 | SDD Review Sign off | 1 day | 29 November 2023 08:00 | 29 November 2023 17:00 | 218 | No
4 | 1.11.5.6 | NFR Design Document | 10 days | 23 October 2023 08:00 | 03 November 2023 17:00 | 219 | No
4 | 1.11.5.7 | NFR Review with ARB | 5 days | 06 November 2023 08:00 | 10 November 2023 17:00 | 220 | No
4 | 1.11.5.8 | NFR Review Updates | 2 days | 13 November 2023 08:00 | 14 November 2023 17:00 | 221 | No
4 | 1.11.5.9 | NFR Final Review | 10 days | 15 November 2023 08:00 | 28 November 2023 17:00 | 222 | No
4 | 1.11.5.10 | NFR Review Sign off | 1 day | 29 November 2023 08:00 | 29 November 2023 17:00 | 223 | No
4 | 1.11.5.11 | Enterprise Architecture (what)/not how at this stage) :- -EA Model, Catalogs & Maps | 28 days | 23 October 2023 08:00 | 29 November 2023 17:00 | 224 | No
5 | 1.11.5.11.1 | Design Document | 10 days | 23 October 2023 08:00 | 03 November 2023 17:00 | 225 | No
5 | 1.11.5.11.2 | Review with ARB | 5 days | 06 November 2023 08:00 | 10 November 2023 17:00 | 226 | No
5 | 1.11.5.11.3 | Review Updates | 2 days | 13 November 2023 08:00 | 14 November 2023 17:00 | 227 | No
5 | 1.11.5.11.4 | Final Review | 10 days | 15 November 2023 08:00 | 28 November 2023 17:00 | 228 | No
5 | 1.11.5.11.5 | Review Sign off | 1 day | 29 November 2023 08:00 | 29 November 2023 17:00 | 229 | No
4 | 1.11.5.12 | Enterprise Architecture (what)/not how at this stage) :- Transition State Architecture | 28 days | 23 October 2023 08:00 | 29 November 2023 17:00 | 230 | No
5 | 1.11.5.12.1 | Design Document | 10 days | 23 October 2023 08:00 | 03 November 2023 17:00 | 231 | No
5 | 1.11.5.12.2 | Review with ARB | 5 days | 06 November 2023 08:00 | 10 November 2023 17:00 | 232 | No
5 | 1.11.5.12.3 | Review Updates | 2 days | 13 November 2023 08:00 | 14 November 2023 17:00 | 233 | No
5 | 1.11.5.12.4 | Final Review | 10 days | 15 November 2023 08:00 | 28 November 2023 17:00 | 234 | No
5 | 1.11.5.12.5 | Review Sign off | 1 day | 29 November 2023 08:00 | 29 November 2023 17:00 | 235 | No
4 | 1.11.5.13 | Test Strategy & Planning | 10 days | 30 June 2023 08:00 | 13 July 2023 17:00 | 236 | No
4 | 1.11.5.14 | Test Strategy & Planning Review | 55 days | 14 July 2023 08:00 | 28 September 2023 17:00 | 237 | No
4 | 1.11.5.15 | Test Strategy & Planning Review Update | 3 days | 29 September 2023 08:00 | 03 October 2023 17:00 | 238 | No
4 | 1.11.5.16 | Test Strategy & Planning Final Review | 3 days | 04 October 2023 08:00 | 06 October 2023 17:00 | 239 | No
4 | 1.11.5.17 | Test Strategy & Planning review Sign off | 1 day | 09 October 2023 08:00 | 09 October 2023 17:00 | 240 | No
4 | 1.11.5.18 | Data Migration Strategy Document | 15 days | 02 October 2023 08:00 | 20 October 2023 17:00 | 241 | No
4 | 1.11.5.19 | Data Migration Strategy Review | 5 days | 23 October 2023 08:00 | 27 October 2023 17:00 | 242 | No
4 | 1.11.5.20 | Data Migration Strategy Review Update | 13 days | 20 September 2023 08:00 | 09 November 2023 12:00 | 243 | No
4 | 1.11.5.21 | Data Migration Strategy Final Review | 10 days | 09 November 2023 13:00 | 23 November 2023 12:00 | 244 | No
4 | 1.11.5.22 | Data Migration Strategy review Sign off | 1 day | 23 November 2023 13:00 | 24 November 2023 12:00 | 245 | No
3 | 1.11.6 | Integration FDDs | 28 days | 08 November 2023 08:00 | 15 December 2023 17:00 | 246 | No
4 | 1.11.6.1 | NICE CXone Customer Account API | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 247 | No
5 | 1.11.6.1.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 248 | No
5 | 1.11.6.1.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 249 | No
5 | 1.11.6.1.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 250 | No
5 | 1.11.6.1.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 251 | No
5 | 1.11.6.1.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 252 | No
5 | 1.11.6.1.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 253 | No
5 | 1.11.6.1.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 254 | No
5 | 1.11.6.1.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 255 | No
5 | 1.11.6.1.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 256 | No
4 | 1.11.6.2 | Contact Us Email Webform Form | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 257 | No
5 | 1.11.6.2.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 258 | No
5 | 1.11.6.2.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 259 | No
5 | 1.11.6.2.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 260 | No
5 | 1.11.6.2.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 261 | No
5 | 1.11.6.2.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 262 | No
5 | 1.11.6.2.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 263 | No
5 | 1.11.6.2.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 264 | No
5 | 1.11.6.2.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 265 | No
5 | 1.11.6.2.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 266 | No
4 | 1.11.6.3 | SMS customer file upload | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 267 | No
5 | 1.11.6.3.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 268 | No
5 | 1.11.6.3.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 269 | No
5 | 1.11.6.3.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 270 | No
5 | 1.11.6.3.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 271 | No
5 | 1.11.6.3.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 272 | No
5 | 1.11.6.3.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 273 | No
5 | 1.11.6.3.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 274 | No
5 | 1.11.6.3.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 275 | No
5 | 1.11.6.3.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 276 | No
4 | 1.11.6.4 | Document Storage | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 277 | No
5 | 1.11.6.4.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 278 | No
5 | 1.11.6.4.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 279 | No
5 | 1.11.6.4.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 280 | No
5 | 1.11.6.4.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 281 | No
5 | 1.11.6.4.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 282 | No
5 | 1.11.6.4.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 283 | No
5 | 1.11.6.4.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 284 | No
5 | 1.11.6.4.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 285 | No
5 | 1.11.6.4.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 286 | No
4 | 1.11.6.5 | Phone call activity creation in D365 CRM | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 287 | No
5 | 1.11.6.5.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 288 | No
5 | 1.11.6.5.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 289 | No
5 | 1.11.6.5.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 290 | No
5 | 1.11.6.5.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 291 | No
5 | 1.11.6.5.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 292 | No
5 | 1.11.6.5.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 293 | No
5 | 1.11.6.5.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 294 | No
5 | 1.11.6.5.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 295 | No
5 | 1.11.6.5.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 296 | No
4 | 1.11.6.6 | Phone call activity updating in D365 CRM | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 297 | No
5 | 1.11.6.6.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 298 | No
5 | 1.11.6.6.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 299 | No
5 | 1.11.6.6.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 300 | No
5 | 1.11.6.6.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 301 | No
5 | 1.11.6.6.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 302 | No
5 | 1.11.6.6.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 303 | No
5 | 1.11.6.6.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 304 | No
5 | 1.11.6.6.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 305 | No
5 | 1.11.6.6.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 306 | No
4 | 1.11.6.7 | Financier Application Integration | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 307 | No
5 | 1.11.6.7.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 308 | No
5 | 1.11.6.7.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 309 | No
5 | 1.11.6.7.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 310 | No
5 | 1.11.6.7.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 311 | No
5 | 1.11.6.7.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 312 | No
5 | 1.11.6.7.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 313 | No
5 | 1.11.6.7.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 314 | No
5 | 1.11.6.7.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 315 | No
5 | 1.11.6.7.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 316 | No
4 | 1.11.6.8 | Customer records pop up when a call is received. | 14 days | 08 November 2023 08:00 | 27 November 2023 17:00 | 317 | No
5 | 1.11.6.8.1 | Documentation of FDD | 2 days | 08 November 2023 08:00 | 09 November 2023 17:00 | 318 | No
5 | 1.11.6.8.2 | FDD Review workshop with users | 1 day | 10 November 2023 08:00 | 10 November 2023 17:00 | 319 | No
5 | 1.11.6.8.3 | FDD Review Updates | 3 days | 13 November 2023 08:00 | 15 November 2023 17:00 | 320 | No
5 | 1.11.6.8.4 | FDD final Review by users | 1 day | 16 November 2023 08:00 | 16 November 2023 17:00 | 321 | No
5 | 1.11.6.8.5 | FDD sign off by users | 1 day | 17 November 2023 08:00 | 17 November 2023 17:00 | 322 | No
5 | 1.11.6.8.6 | FDD Review with ARB | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 323 | No
5 | 1.11.6.8.7 | FDD Review Updates | 1 day | 23 November 2023 08:00 | 23 November 2023 17:00 | 324 | No
5 | 1.11.6.8.8 | FDD Final review with ARB | 1 day | 24 November 2023 08:00 | 24 November 2023 17:00 | 325 | No
5 | 1.11.6.8.9 | FDD sign off by ARB | 1 day | 27 November 2023 08:00 | 27 November 2023 17:00 | 326 | No
4 | 1.11.6.9 | Integration with Adobe Campaign | 14 days | 28 November 2023 08:00 | 15 December 2023 17:00 | 327 | No
5 | 1.11.6.9.1 | Documentation of FDD | 2 days | 28 November 2023 08:00 | 29 November 2023 17:00 | 328 | No
5 | 1.11.6.9.2 | FDD Review workshop with users | 1 day | 30 November 2023 08:00 | 30 November 2023 17:00 | 329 | No
5 | 1.11.6.9.3 | FDD Review Updates | 3 days | 01 December 2023 08:00 | 05 December 2023 17:00 | 330 | No
5 | 1.11.6.9.4 | FDD final Review by users | 1 day | 06 December 2023 08:00 | 06 December 2023 17:00 | 331 | No
5 | 1.11.6.9.5 | FDD sign off by users | 1 day | 07 December 2023 08:00 | 07 December 2023 17:00 | 332 | No
5 | 1.11.6.9.6 | FDD Review with ARB | 3 days | 08 December 2023 08:00 | 12 December 2023 17:00 | 333 | No
5 | 1.11.6.9.7 | FDD Review Updates | 1 day | 13 December 2023 08:00 | 13 December 2023 17:00 | 334 | No
5 | 1.11.6.9.8 | FDD Final review with ARB | 1 day | 14 December 2023 08:00 | 14 December 2023 17:00 | 335 | No
5 | 1.11.6.9.9 | FDD sign off by ARB | 1 day | 15 December 2023 08:00 | 15 December 2023 17:00 | 336 | No
4 | 1.11.6.10 | Integration with Medellia | 10 days | 28 November 2023 08:00 | 11 December 2023 17:00 | 337 | No
5 | 1.11.6.10.1 | Documentation of FDD | 2 days | 28 November 2023 08:00 | 29 November 2023 17:00 | 338 | No
5 | 1.11.6.10.2 | FDD Review workshop with users | 1 day | 30 November 2023 08:00 | 30 November 2023 17:00 | 339 | No
5 | 1.11.6.10.3 | FDD Review Updates | 1 day | 01 December 2023 08:00 | 01 December 2023 17:00 | 340 | No
5 | 1.11.6.10.4 | FDD final Review by users | 1 day | 04 December 2023 08:00 | 04 December 2023 17:00 | 341 | No
5 | 1.11.6.10.5 | FDD sign off by users | 1 day | 05 December 2023 08:00 | 05 December 2023 17:00 | 342 | No
5 | 1.11.6.10.6 | FDD Review with ARB | 1 day | 06 December 2023 08:00 | 06 December 2023 17:00 | 343 | No
5 | 1.11.6.10.7 | FDD Review Updates | 1 day | 07 December 2023 08:00 | 07 December 2023 17:00 | 344 | No
5 | 1.11.6.10.8 | FDD Final review with ARB | 1 day | 08 December 2023 08:00 | 08 December 2023 17:00 | 345 | No
5 | 1.11.6.10.9 | FDD sign off by ARB | 1 day | 11 December 2023 08:00 | 11 December 2023 17:00 | 346 | No
2 | 1.12 | Check Point On Project Status & Plan | 1 day | 12 December 2023 08:00 | 12 December 2023 17:00 | 347 | No
2 | 1.13 | Test Case Scripts preparation | 77 days | 02 October 2023 08:00 | 16 January 2024 17:00 | 348 | No
3 | 1.13.1 | SIT Test Case Preparation | 57 days | 02 October 2023 08:00 | 19 December 2023 17:00 | 349 | No
4 | 1.13.1.1 | Customer Service Milestone Documents | 44 days | 02 October 2023 08:00 | 30 November 2023 17:00 | 350 | No
5 | 1.13.1.1.1 | Test Script Preparation | 30 days | 02 October 2023 08:00 | 10 November 2023 17:00 | 351 | No
5 | 1.13.1.1.2 | Test Script Review | 5 days | 13 November 2023 08:00 | 17 November 2023 17:00 | 352 | No
5 | 1.13.1.1.3 | Test Script Review Update | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 353 | No
5 | 1.13.1.1.4 | Test Script Final Review | 5 days | 23 November 2023 08:00 | 29 November 2023 17:00 | 354 | No
5 | 1.13.1.1.5 | Test Script Review Sign off | 1 day | 30 November 2023 08:00 | 30 November 2023 17:00 | 355 | No
4 | 1.13.1.2 | Marketing Milestone Documents | 24 days | 16 November 2023 08:00 | 19 December 2023 17:00 | 356 | No
5 | 1.13.1.2.1 | Test Scrip Preparation | 10 days | 16 November 2023 08:00 | 29 November 2023 17:00 | 357 | No
5 | 1.13.1.2.2 | Test Script Review | 5 days | 30 November 2023 08:00 | 06 December 2023 17:00 | 358 | No
5 | 1.13.1.2.3 | Test Script Review Update | 3 days | 07 December 2023 08:00 | 11 December 2023 17:00 | 359 | No
5 | 1.13.1.2.4 | Test Script Final Review | 5 days | 12 December 2023 08:00 | 18 December 2023 17:00 | 360 | No
5 | 1.13.1.2.5 | Test Script Review Sign off | 1 day | 19 December 2023 08:00 | 19 December 2023 17:00 | 361 | No
4 | 1.13.1.3 | Financial Services Milestone Documents | 44 days | 02 October 2023 08:00 | 30 November 2023 17:00 | 362 | No
5 | 1.13.1.3.1 | Test Script Preparation | 30 days | 02 October 2023 08:00 | 10 November 2023 17:00 | 363 | No
5 | 1.13.1.3.2 | Test Script Review | 5 days | 13 November 2023 08:00 | 17 November 2023 17:00 | 364 | No
5 | 1.13.1.3.3 | Test Script Review Update | 3 days | 20 November 2023 08:00 | 22 November 2023 17:00 | 365 | No
5 | 1.13.1.3.4 | Test Script Final Review | 5 days | 23 November 2023 08:00 | 29 November 2023 17:00 | 366 | No
5 | 1.13.1.3.5 | Test Script Review Sign off | 1 day | 30 November 2023 08:00 | 30 November 2023 17:00 | 367 | No
3 | 1.13.2 | UAT Test Case Preparation | 33 days | 01 December 2023 08:00 | 16 January 2024 17:00 | 368 | No
4 | 1.13.2.1 | Customer Service | 20 days | 01 December 2023 08:00 | 28 December 2023 17:00 | 369 | No
5 | 1.13.2.1.1 | Test Script Preparation | 20 days | 01 December 2023 08:00 | 28 December 2023 17:00 | 370 | No
4 | 1.13.2.2 | Marketing | 20 days | 20 December 2023 08:00 | 16 January 2024 17:00 | 371 | No
5 | 1.13.2.2.1 | Test Scrip Preparation | 20 days | 20 December 2023 08:00 | 16 January 2024 17:00 | 372 | No
4 | 1.13.2.3 | Financial Services | 20 days | 01 December 2023 08:00 | 28 December 2023 17:00 | 373 | No
5 | 1.13.2.3.1 | Test Script Preparation | 20 days | 01 December 2023 08:00 | 28 December 2023 17:00 | 374 | No
2 | 1.14 | Build | 87 days? | 18 September 2023 08:00 | 16 January 2024 17:00 | 375 | No
3 | 1.14.1 | Configure D365 CRM & Validate | 82 days? | 18 September 2023 08:00 | 09 January 2024 17:00 | 376 | No
4 | 1.14.1.1 | Customer Service & Financial Services | 72 days? | 18 September 2023 08:00 | 26 December 2023 17:00 | 377 | No
5 | 1.14.1.1.1 | Customer Search | 5 days | 18 September 2023 08:00 | 22 September 2023 17:00 | 378 | No
5 | 1.14.1.1.2 | Customer Search Demo 1 | 1 day | 25 September 2023 08:00 | 25 September 2023 17:00 | 379 | No
5 | 1.14.1.1.3 | Knowledge management | 5 days | 26 September 2023 08:00 | 02 October 2023 17:00 | 380 | No
5 | 1.14.1.1.4 | Knowledge Management Demo 2 | 1 day | 09 October 2023 08:00 | 09 October 2023 17:00 | 381 | No
5 | 1.14.1.1.5 | Enquiry Management | 20 days | 03 October 2023 08:00 | 30 October 2023 17:00 | 382 | No
5 | 1.14.1.1.6 | Enquiry Management Demo 3 | 1 day? | 31 October 2023 08:00 | 31 October 2023 17:00 | 383 | No
5 | 1.14.1.1.7 | Requlated Compliant Management | 20 days | 31 October 2023 08:00 | 27 November 2023 17:00 | 384 | No
5 | 1.14.1.1.8 | Regulated Compliant Management Demo 4 | 1 day? | 28 November 2023 08:00 | 28 November 2023 17:00 | 385 | No
5 | 1.14.1.1.9 | Non Regulated Complaint Management | 20 days | 31 October 2023 08:00 | 27 November 2023 17:00 | 386 | No
5 | 1.14.1.1.10 | Non Regulated Compliant Management Demo 5 | 1 day | 28 November 2023 08:00 | 28 November 2023 17:00 | 387 | No
5 | 1.14.1.1.11 | Activity Management | 40 days | 10 October 2023 08:00 | 04 December 2023 17:00 | 388 | No
5 | 1.14.1.1.12 | Activity Management Demo 6 | 1 day? | 05 December 2023 08:00 | 05 December 2023 17:00 | 389 | No
5 | 1.14.1.1.13 | SLA Management | 40 days | 31 October 2023 08:00 | 25 December 2023 17:00 | 390 | No
5 | 1.14.1.1.14 | SLA Management Demo 7 | 1 day | 26 December 2023 08:00 | 26 December 2023 17:00 | 391 | No
5 | 1.14.1.1.15 | Queue Management | 40 days | 10 October 2023 08:00 | 04 December 2023 17:00 | 392 | No
5 | 1.14.1.1.16 | Queue Management Demo 8 | 1 day | 05 December 2023 08:00 | 05 December 2023 17:00 | 393 | No
5 | 1.14.1.1.17 | Reports & Dashboards | 50 days | 10 October 2023 08:00 | 18 December 2023 17:00 | 394 | No
5 | 1.14.1.1.18 | Reports & Dashboards | 1 day? | 19 December 2023 08:00 | 19 December 2023 17:00 | 395 | No
4 | 1.14.1.2 | Marketing | 26 days | 16 November 2023 08:00 | 21 December 2023 17:00 | 396 | No
5 | 1.14.1.2.1 | Campaign Analysis Process | 15 days | 16 November 2023 08:00 | 06 December 2023 17:00 | 397 | No
5 | 1.14.1.2.2 | Mkt - Customer Demo 1 | 1 day | 07 December 2023 08:00 | 07 December 2023 17:00 | 398 | No
5 | 1.14.1.2.3 | Reports & Analysis Process | 10 days | 07 December 2023 08:00 | 20 December 2023 17:00 | 399 | No
5 | 1.14.1.2.4 | Mkt - Customer Demo 2 | 1 day | 21 December 2023 08:00 | 21 December 2023 17:00 | 400 | No
4 | 1.14.1.3 | Integrations | 29 days | 28 November 2023 08:00 | 05 January 2024 17:00 | 401 | No
5 | 1.14.1.3.1 | Data Mapping | 5 days | 13 December 2023 08:00 | 19 December 2023 17:00 | 402 | No
5 | 1.14.1.3.2 | Development | 29 days | 28 November 2023 08:00 | 05 January 2024 17:00 | 403 | No
6 | 1.14.1.3.2.1 | NICE CXone Customer Account API | 5 days | 01 January 2024 08:00 | 05 January 2024 17:00 | 404 | No
6 | 1.14.1.3.2.2 | Contact Us Email Webform Form | 5 days | 28 November 2023 08:00 | 04 December 2023 17:00 | 405 | No
6 | 1.14.1.3.2.3 | SMS customer file upload | 5 days | 05 December 2023 08:00 | 11 December 2023 17:00 | 406 | No
6 | 1.14.1.3.2.4 | Document Storage | 5 days | 12 December 2023 08:00 | 18 December 2023 17:00 | 407 | No
6 | 1.14.1.3.2.5 | Phone call activity creation in D365 CRM | 5 days | 01 January 2024 08:00 | 05 January 2024 17:00 | 408 | No
6 | 1.14.1.3.2.6 | Phone call activity updating in D365 CRM | 5 days | 01 January 2024 08:00 | 05 January 2024 17:00 | 409 | No
6 | 1.14.1.3.2.7 | Financier Application Integration | 15 days | 28 November 2023 08:00 | 18 December 2023 17:00 | 410 | No
6 | 1.14.1.3.2.8 | Customer records pop up when a call is received. | 5 days | 01 January 2024 08:00 | 05 January 2024 17:00 | 411 | No
6 | 1.14.1.3.2.9 | Integration with Adobe Campaign | 10 days | 22 December 2023 08:00 | 04 January 2024 17:00 | 412 | No
6 | 1.14.1.3.2.10 | Integration with Medellia | 1 day | 22 December 2023 08:00 | 22 December 2023 17:00 | 413 | No
4 | 1.14.1.4 | Data migration | 50 days | 01 November 2023 08:00 | 09 January 2024 17:00 | 414 | No
5 | 1.14.1.4.1 | Data Mapping | 5 days | 01 November 2023 08:00 | 07 November 2023 17:00 | 415 | No
5 | 1.14.1.4.2 | Master data import to D365 CRM | 35 days | 08 November 2023 08:00 | 26 December 2023 17:00 | 416 | No
5 | 1.14.1.4.3 | Master data validation | 10 days | 27 December 2023 08:00 | 09 January 2024 17:00 | 417 | No
3 | 1.14.2 | Unit Testing | 81 days | 26 September 2023 08:00 | 16 January 2024 17:00 | 418 | No
4 | 1.14.2.1 | Customer Service & Financial Services | 69 days | 26 September 2023 08:00 | 29 December 2023 17:00 | 419 | No
5 | 1.14.2.1.1 | Customer Search | 2 days | 26 September 2023 08:00 | 27 September 2023 17:00 | 420 | No
5 | 1.14.2.1.2 | Knowledge Management | 3 days | 10 October 2023 08:00 | 12 October 2023 17:00 | 421 | No
5 | 1.14.2.1.3 | Enquiry Management | 3 days | 01 November 2023 08:00 | 03 November 2023 17:00 | 422 | No
5 | 1.14.2.1.4 | Regulated Compliant Management | 3 days | 29 November 2023 08:00 | 01 December 2023 17:00 | 423 | No
5 | 1.14.2.1.5 | Non Regulated Compliant Management | 3 days | 29 November 2023 08:00 | 01 December 2023 17:00 | 424 | No
5 | 1.14.2.1.6 | Activity Management | 3 days | 06 December 2023 08:00 | 08 December 2023 17:00 | 425 | No
5 | 1.14.2.1.7 | SLA Management | 3 days | 27 December 2023 08:00 | 29 December 2023 17:00 | 426 | No
5 | 1.14.2.1.8 | Queue Management | 3 days | 06 December 2023 08:00 | 08 December 2023 17:00 | 427 | No
5 | 1.14.2.1.9 | Reports & Dashboards | 14 days | 05 December 2023 08:00 | 22 December 2023 17:00 | 428 | No
4 | 1.14.2.2 | Marketing | 19 days | 08 December 2023 08:00 | 03 January 2024 17:00 | 429 | No
5 | 1.14.2.2.1 | Campaign Analysis Process | 5 days | 08 December 2023 08:00 | 14 December 2023 17:00 | 430 | No
5 | 1.14.2.2.2 | Reports & Analysis Process | 10 days | 21 December 2023 08:00 | 03 January 2024 17:00 | 431 | No
4 | 1.14.2.3 | Integrations | 27 days | 05 December 2023 08:00 | 10 January 2024 17:00 | 432 | No
5 | 1.14.2.3.1 | Validations of APIs | 27 days | 05 December 2023 08:00 | 10 January 2024 17:00 | 433 | No
6 | 1.14.2.3.1.1 | NICE CXone Customer Account API | 3 days | 08 January 2024 08:00 | 10 January 2024 17:00 | 434 | No
6 | 1.14.2.3.1.2 | Contact Us Email Webform Form | 3 days | 05 December 2023 08:00 | 07 December 2023 17:00 | 435 | No
6 | 1.14.2.3.1.3 | SMS customer file upload | 3 days | 12 December 2023 08:00 | 14 December 2023 17:00 | 436 | No
6 | 1.14.2.3.1.4 | Financier Integration | 10 days | 19 December 2023 08:00 | 01 January 2024 17:00 | 437 | No
6 | 1.14.2.3.1.5 | Document Storage | 3 days | 19 December 2023 08:00 | 21 December 2023 17:00 | 438 | No
6 | 1.14.2.3.1.6 | Phone call activity creation in D365 CRM | 3 days | 08 January 2024 08:00 | 10 January 2024 17:00 | 439 | No
6 | 1.14.2.3.1.7 | Phone call activity updating in D365 CRM | 3 days | 08 January 2024 08:00 | 10 January 2024 17:00 | 440 | No
6 | 1.14.2.3.1.8 | Integration with Adobe Campaign | 3 days | 05 January 2024 08:00 | 09 January 2024 17:00 | 441 | No
6 | 1.14.2.3.1.9 | Integration with Medellia | 3 days | 25 December 2023 08:00 | 27 December 2023 17:00 | 442 | No
6 | 1.14.2.3.1.10 | Customer records pop up when a call is received. | 3 days | 08 January 2024 08:00 | 10 January 2024 17:00 | 443 | No
4 | 1.14.2.4 | Data migration | 40 days | 22 November 2023 08:00 | 16 January 2024 17:00 | 444 | No
5 | 1.14.2.4.1 | Master data import to D365 CRM | 10 days | 22 November 2023 08:00 | 05 December 2023 17:00 | 445 | No
5 | 1.14.2.4.2 | Master data validation | 30 days | 06 December 2023 08:00 | 16 January 2024 17:00 | 446 | No
2 | 1.15 | Milestone Delivery | 26 days | 10 January 2024 08:00 | 14 February 2024 17:00 | 447 | No
3 | 1.15.1 | Technical Build Document | 10 days | 10 January 2024 08:00 | 23 January 2024 17:00 | 448 | No
3 | 1.15.2 | Technical Build Review | 5 days | 24 January 2024 08:00 | 30 January 2024 17:00 | 449 | No
3 | 1.15.3 | Technical Build Review Update | 5 days | 31 January 2024 08:00 | 06 February 2024 17:00 | 450 | No
3 | 1.15.4 | Technical Build Final Review | 5 days | 07 February 2024 08:00 | 13 February 2024 17:00 | 451 | No
3 | 1.15.5 | Technical Build review Sign off | 1 day | 14 February 2024 08:00 | 14 February 2024 17:00 | 452 | No
2 | 1.16 | SIT Environment Setup | 15 days | 10 October 2023 08:00 | 30 October 2023 17:00 | 453 | No
3 | 1.16.1 | SIT Setup | 15 days | 10 October 2023 08:00 | 30 October 2023 17:00 | 454 | No
2 | 1.17 | Perform SIT | 57 days | 06 November 2023 08:00 | 23 January 2024 17:00 | 455 | No
3 | 1.17.1 | SIT test validation | 56 days | 06 November 2023 08:00 | 22 January 2024 17:00 | 456 | No
4 | 1.17.1.1 | Customer Service & Financial Services | 40 days | 06 November 2023 08:00 | 29 December 2023 17:00 | 457 | No
5 | 1.17.1.1.1 | Customer Search | 5 days | 06 November 2023 08:00 | 10 November 2023 17:00 | 458 | No
5 | 1.17.1.1.2 | Knowledge Management | 5 days | 13 November 2023 08:00 | 17 November 2023 17:00 | 459 | No
5 | 1.17.1.1.3 | Enquiry Management | 15 days | 20 November 2023 08:00 | 08 December 2023 17:00 | 460 | No
5 | 1.17.1.1.4 | Regulated Compliant Management | 15 days | 04 December 2023 08:00 | 22 December 2023 17:00 | 461 | No
5 | 1.17.1.1.5 | Non Regulated Compliant Management | 15 days | 04 December 2023 08:00 | 22 December 2023 17:00 | 462 | No
5 | 1.17.1.1.6 | Activity Management | 10 days | 04 December 2023 08:00 | 15 December 2023 17:00 | 463 | No
5 | 1.17.1.1.7 | SLA Management | 10 days | 04 December 2023 08:00 | 15 December 2023 17:00 | 464 | No
5 | 1.17.1.1.8 | Queue Management | 10 days | 04 December 2023 08:00 | 15 December 2023 17:00 | 465 | No
5 | 1.17.1.1.9 | Reports & Dashboards | 20 days | 04 December 2023 08:00 | 29 December 2023 17:00 | 466 | No
4 | 1.17.1.2 | Marketing | 10 days | 04 January 2024 08:00 | 17 January 2024 17:00 | 467 | No
5 | 1.17.1.2.1 | Campaign Analysis Process | 5 days | 04 January 2024 08:00 | 10 January 2024 17:00 | 468 | No
5 | 1.17.1.2.2 | Reports & Analysis Process | 10 days | 04 January 2024 08:00 | 17 January 2024 17:00 | 469 | No
4 | 1.17.1.3 | Integrations | 54 days | 06 November 2023 08:00 | 18 January 2024 17:00 | 470 | No
5 | 1.17.1.3.1 | Validations of APIs | 54 days | 06 November 2023 08:00 | 18 January 2024 17:00 | 471 | No
6 | 1.17.1.3.1.1 | NICE CXone Customer Account API | 3 days | 11 January 2024 08:00 | 15 January 2024 17:00 | 472 | No
6 | 1.17.1.3.1.2 | Contact Us Email Webform Form | 3 days | 06 November 2023 08:00 | 08 November 2023 17:00 | 473 | No
6 | 1.17.1.3.1.3 | SMS customer file upload | 3 days | 15 December 2023 08:00 | 19 December 2023 17:00 | 474 | No
6 | 1.17.1.3.1.4 | Financier Integration | 10 days | 02 January 2024 08:00 | 15 January 2024 17:00 | 475 | No
6 | 1.17.1.3.1.5 | Document Storage | 3 days | 22 December 2023 08:00 | 26 December 2023 17:00 | 476 | No
6 | 1.17.1.3.1.6 | Phone call activity creation in D365 CRM | 3 days | 11 January 2024 08:00 | 15 January 2024 17:00 | 477 | No
6 | 1.17.1.3.1.7 | Phone call activity updating in D365 CRM | 3 days | 11 January 2024 08:00 | 15 January 2024 17:00 | 478 | No
6 | 1.17.1.3.1.8 | Integration with Adobe Campaign | 3 days | 10 January 2024 08:00 | 12 January 2024 17:00 | 479 | No
6 | 1.17.1.3.1.9 | Integration with Medellia | 3 days | 28 December 2023 08:00 | 01 January 2024 17:00 | 480 | No
6 | 1.17.1.3.1.10 | Customer records pop up when a call is received. | 6 days | 11 January 2024 08:00 | 18 January 2024 17:00 | 481 | No
4 | 1.17.1.4 | Data migration | 34 days | 06 December 2023 08:00 | 22 January 2024 17:00 | 482 | No
5 | 1.17.1.4.1 | Master data import to D365 CRM | 33 days | 06 December 2023 08:00 | 19 January 2024 17:00 | 483 | No
5 | 1.17.1.4.2 | Master data validation | 19 days | 27 December 2023 08:00 | 22 January 2024 17:00 | 484 | No
3 | 1.17.2 | SIT fix | 51 days | 06 November 2023 08:00 | 15 January 2024 17:00 | 485 | No
3 | 1.17.3 | Bug fixes, if any | 5 days | 16 January 2024 08:00 | 22 January 2024 17:00 | 486 | No
3 | 1.17.4 | Issue log signoff | 1 day | 23 January 2024 08:00 | 23 January 2024 17:00 | 487 | No
2 | 1.18 | End to End SIT Testing | 21 days | 24 January 2024 08:00 | 21 February 2024 17:00 | 488 | No
3 | 1.18.1 | End to End Testing | 21 days | 24 January 2024 08:00 | 21 February 2024 17:00 | 489 | No
2 | 1.19 | Training | 40 days | 31 January 2024 08:00 | 26 March 2024 17:00 | 490 | No
3 | 1.19.1 | Preparation of training documents | 40 days | 31 January 2024 08:00 | 26 March 2024 17:00 | 491 | No
3 | 1.19.2 | Train the trainers | 5 days | 22 February 2024 08:00 | 28 February 2024 17:00 | 492 | No
2 | 1.20 | Business Change | 108 days? | 29 December 2023 08:00 | 28 May 2024 17:00 | 493 | No
3 | 1.20.1 | Change Impact Assesment | 15 days | 29 December 2023 08:00 | 18 January 2024 17:00 | 494 | No
4 | 1.20.1.1 | Training Approach/Strategy (external providers to deliver training, volumes, material, train the trainer) | 5 days | 29 December 2023 08:00 | 04 January 2024 17:00 | 495 | No
4 | 1.20.1.2 | Coms approach/strategy (external parties, timings, volumes, types) | 5 days | 05 January 2024 08:00 | 11 January 2024 17:00 | 496 | No
4 | 1.20.1.3 | Identify key stakeholders | 5 days | 12 January 2024 08:00 | 18 January 2024 17:00 | 497 | No
3 | 1.20.2 | Training | 104 days? | 04 January 2024 08:00 | 28 May 2024 17:00 | 498 | No
4 | 1.20.2.1 | Create training material | 86 days | 04 January 2024 08:00 | 02 May 2024 17:00 | 499 | No
4 | 1.20.2.2 | Organise training (Rooms, invites, booking trainers) | 5 days | 05 March 2024 08:00 | 11 March 2024 17:00 | 500 | No
4 | 1.20.2.3 | Execute training | 30 days | 16 April 2024 08:00 | 27 May 2024 17:00 | 501 | No
4 | 1.20.2.4 | Lessons learnt feedback | 1 day? | 28 May 2024 08:00 | 28 May 2024 17:00 | 502 | No
3 | 1.20.3 | Comms | 40 days | 31 January 2024 08:00 | 26 March 2024 17:00 | 503 | No
4 | 1.20.3.1 | Create Comms material | 20 days | 31 January 2024 08:00 | 27 February 2024 17:00 | 504 | No
4 | 1.20.3.2 | Organise comms sessions (invites, rooms, distribution list) | 5 days | 28 February 2024 08:00 | 05 March 2024 17:00 | 505 | No
4 | 1.20.3.3 | Execute comms (send eail, present at huddle etc | 5 days | 06 March 2024 08:00 | 12 March 2024 17:00 | 506 | No
4 | 1.20.3.4 | For all project team members (incuding UAT) , FGH and Tech M, there needs to be a comms plan for onboarding the colleagues into the project to explain what is expected | 10 days | 13 March 2024 08:00 | 26 March 2024 17:00 | 507 | No
3 | 1.20.4 | Leadership | 10 days | 27 March 2024 08:00 | 09 April 2024 17:00 | 508 | No
4 | 1.20.4.1 | Work with Key stakeholders (SMT/SME's) to influence change delivery (Open door sessions, regular check ins, listening sessions)(receive not transmit) | 10 days | 27 March 2024 08:00 | 09 April 2024 17:00 | 509 | No
2 | 1.21 | UAT Environment Setup | 5 days | 24 January 2024 08:00 | 30 January 2024 17:00 | 510 | No
3 | 1.21.1 | UAT Setup | 5 days | 24 January 2024 08:00 | 30 January 2024 17:00 | 511 | No
2 | 1.22 | User acceptance testing | 52 days | 31 January 2024 08:00 | 11 April 2024 17:00 | 512 | No
3 | 1.22.1 | Data Migration Upload | 10 days | 31 January 2024 08:00 | 13 February 2024 17:00 | 513 | No
3 | 1.22.2 | Deployment of Configuration & Customization | 5 days | 31 January 2024 08:00 | 06 February 2024 17:00 | 514 | No
3 | 1.22.3 | UAT testing by superuser | 30 days | 01 March 2024 08:00 | 11 April 2024 17:00 | 515 | No
3 | 1.22.4 | Users – validate the solution | 30 days | 29 February 2024 08:00 | 10 April 2024 17:00 | 516 | No
3 | 1.22.5 | Assist users during UAT | 30 days | 29 February 2024 08:00 | 10 April 2024 17:00 | 517 | No
3 | 1.22.6 | UAT feedback and fix | 30 days | 29 February 2024 08:00 | 10 April 2024 17:00 | 518 | No
3 | 1.22.7 | UAT Sign Off | 1 day | 11 April 2024 08:00 | 11 April 2024 17:00 | 519 | No
2 | 1.23 | Code Freeze (Build readiness) | 1 day | 12 April 2024 08:00 | 12 April 2024 17:00 | 520 | No
2 | 1.24 | Production Environment Setup | 5 days | 15 April 2024 08:00 | 19 April 2024 17:00 | 521 | No
3 | 1.24.1 | Production Setup | 5 days | 15 April 2024 08:00 | 19 April 2024 17:00 | 522 | No
2 | 1.25 | Pre-Go Live checklist/Cut-over | 89 days? | 16 January 2024 08:00 | 17 May 2024 17:00 | 523 | No
3 | 1.25.1 | Go/No-Go UAT signoff | 1 day | 12 April 2024 08:00 | 12 April 2024 17:00 | 524 | No
3 | 1.25.2 | Cut Over Workshop | 1 day? | 16 January 2024 08:00 | 16 January 2024 17:00 | 525 | No
3 | 1.25.3 | CutOver Strategy Document preparation | 5 days | 17 January 2024 08:00 | 23 January 2024 17:00 | 526 | No
3 | 1.25.4 | Cut over strategy document review | 5 days | 24 January 2024 08:00 | 30 January 2024 17:00 | 527 | No
3 | 1.25.5 | Cutover Strategy Sign off | 1 day? | 31 January 2024 08:00 | 31 January 2024 17:00 | 528 | No
3 | 1.25.6 | Pre-Go Live Activitiies | 20 days | 22 April 2024 08:00 | 17 May 2024 17:00 | 529 | No
4 | 1.25.6.1 | Deploy Configurations & Customizations to Production | 5 days | 22 April 2024 08:00 | 26 April 2024 17:00 | 530 | No
4 | 1.25.6.2 | Integrations | 10 days | 22 April 2024 08:00 | 03 May 2024 17:00 | 531 | No
4 | 1.25.6.3 | Data upload | 15 days | 22 April 2024 08:00 | 10 May 2024 17:00 | 532 | No
4 | 1.25.6.4 | Sanity check | 5 days | 13 May 2024 08:00 | 17 May 2024 17:00 | 533 | No
2 | 1.26 | Go-live | 1 day | 20 May 2024 08:00 | 20 May 2024 17:00 | 534 | No
3 | 1.26.1 | Go-Live | 1 day | 20 May 2024 08:00 | 20 May 2024 17:00 | 535 | No
2 | 1.27 | Project Closure | 1 day? | 21 May 2024 08:00 | 21 May 2024 17:00 | 536 | No
3 | 1.27.1 | Project Closure - Introspection meeting | 1 day? | 21 May 2024 08:00 | 21 May 2024 17:00 | 537 | No