## UK-View-DATimeline
Task Name | Task Name (Base) | Who | Include Who? | Include Date? | Visual Flag | Duration | Start | Finish | Predecessors | Visual Text | Visual Swimlane | Visual Track # Within Swimlane | Visual # Tracks To Cover | Text Layout | Format String | Done Format String | Assigned To | % Complete | Status | Comments
PLAN START | PLAN START |  |  |  |  | 0 | 2021-10-01 | 2021-10-01
Review / sign off data spec | Review / sign off data spec | DAs, DDTS, LI |  |  | TRUE | 20d | 2021-10-01 | 2021-10-28 | 1
Data spec agreed | Data spec agreed | DAs, DDTS, LI |  |  | TRUE | 0 | 2021-10-28 | 2021-10-28 | 2
Agree technical delivery mechanism from DA to DDTS | Agree technical delivery mechanism from DA to DDTS | DAs, DDTS |  |  | TRUE | 15d | 2021-10-01 | 2021-10-21 | 1
Technical delivery mechanism from DA to DDTS agreed | Technical delivery mechanism from DA to DDTS agreed | DAs, DDTS |  |  | TRUE | 0 | 2021-10-21 | 2021-10-21 | 4
Agree technical delivery mechanism from DDTS to UK View | Agree technical delivery mechanism from DDTS to UK View | DDTS, LI |  |  | TRUE | 15d | 2021-10-01 | 2021-10-21 | 4SS
Technical delivery mechanism from DDTS to UK View agreed | Technical delivery mechanism from DDTS to UK View agreed | DDTS, LI |  |  | TRUE | 0 | 2021-10-21 | 2021-10-21 | 6
Agree technical format for live data extract from DAs to LI, DDTS | Agree technical format for live data extract from DAs to LI, DDTS | DAs, DDTS, LI |  |  | TRUE | 15d | 2021-10-01 | 2021-10-21 | 4SS
Technical format for live data extract from DAs to LI, DDTS agreed | Technical format for live data extract from DAs to LI, DDTS agreed | DAs, DDTS, LI |  |  | TRUE | 0 | 2021-10-21 | 2021-10-21 | 8
DAs create live data extract to LI and DDTS conforming to data spec. | DAs create live data extract to LI and DDTS conforming to data spec. | DAs, DDTS, LI |  |  | TRUE | 20d | 2021-10-22 | 2021-11-18 | 9
Live data extract to LI and DDTS available | Live data extract to LI and DDTS available | DAs, DDTS, LI |  |  | TRUE | 0 | 2021-11-18 | 2021-11-18 | 10
Build DA -> DDTS dev/test feed (DA end) | Build DA -> DDTS dev/test feed (DA end) | DAs |  |  | TRUE | 20d | 2021-10-21 | 2021-11-18 | 9SS
DA -> DDTS dev/test feed (DA end) available to DDTS | DA -> DDTS dev/test feed (DA end) available to DDTS |  |  |  | TRUE | 1d | 2021-10-21 | 2021-10-22 | 9SS
Build DA -> DDTS dev/test feed (DDTS end) | Build DA -> DDTS dev/test feed (DDTS end) | DDTS |  |  | TRUE | 20d | 2021-10-21 | 2021-11-18 | 9SS
Build DDTS -> UKV dev/test feed (DDTS end) | Build DDTS -> UKV dev/test feed (DDTS end) | DDTS |  |  | TRUE | 20d | 2021-10-21 | 2021-11-18 | 9SS
Build DDTS -> UKV dev/test feed (UKV end) | Build DDTS -> UKV dev/test feed (UKV end) | LI |  |  | TRUE | 20d | 2021-10-21 | 2021-11-18 | 9SS
Build UKV Reports (Pre-feed 60%) | Build UKV Reports (Pre-feed 60%) | LI |  |  | TRUE | 20d | 2021-10-21 | 2021-11-18 | 9SS
Build UKV Reports (Post-feed 40%) | Build UKV Reports (Post-feed 40%) | LI |  |  | TRUE | 20d | 2021-10-21 | 2021-11-18 | 9SS
UKV UAT | UKV UAT | LI, APHA, DAs, DDTS |  |  | TRUE | 30d | 2021-10-21 | 2021-12-02 | 9SS
Deploy to Production | Deploy to Production |  |  |  | TRUE | 10d | 2021-12-02 | 2021-12-16 | 19
UK View Live | UK View Live |  |  |  | TRUE | 0 | 2021-12-16 | 2021-12-16 | 20