## UK-View-Delivery
Unique Sticky ID | Task Name | Duration | Start | Finish | Predecessors | Visual Flag | Visual Text | Visual Swimlane | Visual Track # Within Swimlane | Visual # Tracks To Cover | Text Layout | Format String | Done Format String | Assigned To | % Complete | Status | Comments | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17
ID-001 | Agile Delivery | 290d | 2021-06-16 | 2022-07-26
ID-002 | Sprints | 290d | 2021-06-16 | 2022-07-26
ID-003 | S10 | 10d | 2021-06-16 | 2021-06-29
ID-004 | S11 | 10d | 2021-06-30 | 2021-07-13
ID-005 | S12 | 10d | 2021-07-14 | 2021-07-27
ID-006 | S13 | 10d | 2021-07-28 | 2021-08-10 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-007 | S14 | 10d | 2021-08-11 | 2021-08-24 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-008 | S15 | 10d | 2021-08-25 | 2021-09-07 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-009 | S16 | 10d | 2021-09-08 | 2021-09-21 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-010 | S17 | 10d | 2021-09-22 | 2021-10-05 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-011 | S18 | 10d | 2021-10-06 | 2021-10-19 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-012 | S19 | 10d | 2021-10-20 | 2021-11-02 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-013 | S20 | 10d | 2021-11-03 | 2021-11-16 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-014 | S21 | 10d | 2021-11-17 | 2021-11-30 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-015 | S22 | 10d | 2021-12-01 | 2021-12-14 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-016 | S23 | 10d | 2021-12-15 | 2021-12-28 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-017 | S24 | 10d | 2021-12-29 | 2022-01-11 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-018 | S25 | 10d | 2022-01-12 | 2022-01-25 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-019 | S26 | 10d | 2022-01-26 | 2022-02-08 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-020 | S27 | 10d | 2022-02-09 | 2022-02-22 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-021 | S28 | 10d | 2022-02-23 | 2022-03-08 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-022 | S29 | 10d | 2022-03-09 | 2022-03-22 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-023 | S30 | 10d | 2022-03-23 | 2022-04-05 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-024 | S31 | 10d | 2022-04-06 | 2022-04-19 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-025 | S32 | 10d | 2022-04-20 | 2022-05-03 |  | TRUE |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-026 | S33 | 10d | 2022-05-04 | 2022-05-17 |  |  |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-027 | S34 | 10d | 2022-05-18 | 2022-05-31 |  |  |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-028 | S35 | 10d | 2022-06-01 | 2022-06-14 |  |  |  | Agile Sprints | 1 |  | Centre | Sprint-Odd
ID-029 | S36 | 10d | 2022-06-15 | 2022-06-28 |  |  |  | Agile Sprints | 1 |  | Centre | Sprint-Even
ID-030 | S37 | 10d | 2022-06-29 | 2022-07-12
ID-031 | S38 | 10d | 2022-07-13 | 2022-07-26
ID-032 | Sprint End Milestones | 280d | 2021-06-29 | 2022-07-26
ID-033 | 10 | 0 | 2021-06-29 | 2021-06-29
ID-034 | 11 | 0 | 2021-07-13 | 2021-07-13
ID-035 | 12 | 0 | 2021-07-27 | 2021-07-27
ID-036 | 13 | 0 | 2021-08-10 | 2021-08-10
ID-037 | 14 | 0 | 2021-08-24 | 2021-08-24
ID-038 | 15 | 0 | 2021-09-07 | 2021-09-07
ID-039 | 16 | 0 | 2021-09-21 | 2021-09-21
ID-040 | 17 | 0 | 2021-10-05 | 2021-10-05
ID-041 | 18 | 0 | 2021-10-19 | 2021-10-19
ID-042 | 19 | 0 | 2021-11-02 | 2021-11-02
ID-043 | 20 | 0 | 2021-11-16 | 2021-11-16
ID-044 | 21 | 0 | 2021-11-30 | 2021-11-30
ID-045 | 22 | 0 | 2021-12-14 | 2021-12-14
ID-046 | 23 (Xmas) | 0 | 2021-12-28 | 2021-12-28
ID-047 | 24 (NewYear) | 0 | 2022-01-11 | 2022-01-11
ID-048 | 25 | 0 | 2022-01-25 | 2022-01-25
ID-049 | 26 | 0 | 2022-02-08 | 2022-02-08
ID-050 | 27 | 0 | 2022-02-22 | 2022-02-22
ID-051 | 28 | 0 | 2022-03-08 | 2022-03-08
ID-052 | 29 | 0 | 2022-03-22 | 2022-03-22
ID-053 | 30 | 0 | 2022-04-05 | 2022-04-05
ID-054 | 31 | 0 | 2022-04-19 | 2022-04-19
ID-055 | 32 | 0 | 2022-05-03 | 2022-05-03
ID-056 | 33 | 0 | 2022-05-17 | 2022-05-17
ID-057 | 34 | 0 | 2022-05-31 | 2022-05-31
ID-058 | 35 | 0 | 2022-06-14 | 2022-06-14
ID-059 | 36 | 0 | 2022-06-28 | 2022-06-28
ID-060 | 37 | 0 | 2022-07-12 | 2022-07-12
ID-061 | 38 | 0 | 2022-07-26 | 2022-07-26
ID-062 | Increments | 210d | 2021-06-16 | 2022-04-05
ID-063 | KBT-I01 | 30d | 2021-06-16 | 2021-07-27
ID-064 | KBT-I02 | 30d | 2021-07-28 | 2021-09-07
ID-065 | KBT-I03 | 30d | 2021-09-08 | 2021-10-19
ID-066 | KBT-I04 | 30d | 2021-10-20 | 2021-11-30
ID-067 | KBT-I05 | 30d | 2021-12-01 | 2022-01-11
ID-068 | KBT-I06 | 30d | 2022-01-12 | 2022-02-22
ID-069 | KBT-I07 | 30d | 2022-02-23 | 2022-04-05
ID-070 | Increment End Milestones | 180d | 2021-07-27 | 2022-04-05
ID-071 | KBT-I01-End | 0 | 2021-07-27 | 2021-07-27
ID-072 | KBT-I02-End | 0 | 2021-09-07 | 2021-09-07
ID-073 | KBT-I03-End | 0 | 2021-10-19 | 2021-10-19
ID-074 | KBT-I04-End | 0 | 2021-11-30 | 2021-11-30
ID-075 | KBT-I05-End | 0 | 2022-01-11 | 2022-01-11
ID-076 | KBT-I06-End | 0 | 2022-02-22 | 2022-02-22
ID-077 | KBT-I07-End | 0 | 2022-04-05 | 2022-04-05
ID-078 | Dependencies | 89d | 2021-07-28 | 2021-11-30 |  |  |  | Dependencies | 2 |  |  | Dark Red
ID-079 | Project Start Date | 0 | 2021-07-28 | 2021-07-28 |  |  |  | Dependencies | 3 |  |  | Dark Blue
ID-080 | ScotEID begin work on UK View integration | 0 | 2021-11-30 | 2021-11-30 |  | TRUE |  | Dependencies | 2 |  |  | Dark Blue (M)
ID-081 | EIDCymru begin work on UK View integration | 0 | 2021-10-05 | 2021-10-05 |  | TRUE |  | Dependencies | 1 |  |  | Dark Blue (M)
ID-082 | Data | 101d | 2021-05-18 | 2021-10-05
ID-083 | UK View Data Modelling | 40d | 2021-08-11 | 2021-10-05 |  |  |  | Integration | 3 |  |  | Amber
ID-084 | Data Modelling 1 (Pre-Spec) | 20d | 2021-08-11 | 2021-09-07 | 103FF | TRUE |  | MVP Build | 3 |  |  | Amber
ID-085 | Data Modelling 2 (Post Spec) | 20d | 2021-09-08 | 2021-10-05 | 84 | TRUE |  | MVP Build | 3 |  | Right | Amber
ID-086 | Test Data | 72d | 2021-05-18 | 2021-08-25
ID-087 | Live data extract available | 72d | 2021-05-18 | 2021-08-25
ID-088 | England live (sheep) data extract available (ARAMS/CLA ??) | 0 | 2021-08-25 | 2021-08-25 | 7FS +1d | TRUE |  | Dependencies | 2 |  |  | Dark Blue (M)
ID-089 | Scotland sheep (early) live data extract available | 0 | 2021-05-18 | 2021-05-18 |  | TRUE |  | Dependencies | 3 |  | Right | Dark Blue (M)
ID-090 | Scotland sheep (comprehensive) live data extract available | 0 | 2021-08-25 | 2021-08-25 | 7FS +1d | TRUE |  | Dependencies | 3 |  | Right | Dark Blue (M)
ID-091 | Wales sheep live data extract available | 0 | 2021-08-25 | 2021-08-25 | 7FS +1d | TRUE |  | Dependencies | 4 |  |  | Dark Blue (M)
ID-092 | Live integration data available
ID-093 | England live integration data available
ID-094 | Scotland live integration data available
ID-095 | Wales live integration data available
ID-096 | DA Integration | 139d | 2021-07-28 | 2022-02-07
ID-097 | Integration Design | 60d | 2021-07-28 | 2021-10-19
ID-098 | Integration Data Design | 50d | 2021-07-28 | 2021-10-05 |  |  |  | Integration | 2 |  |  | Summary Bar
ID-099 | Develop Integration Data Spec. | 50d | 2021-07-28 | 2021-10-05
ID-100 | Develop Integration Data Spec | 50d | 2021-07-28 | 2021-10-05 |  |  |  | Integration | 4 |  |  | Amber
ID-101 | Develop integration data requirements | 20d | 2021-07-28 | 2021-08-24 | 79 | TRUE |  | Integration | 1 |  |  | Amber
ID-102 | Develop draft MVP integration spec | 20d | 2021-08-11 | 2021-09-07 | 101SS +10d | TRUE |  | Integration | 2 |  |  | Amber
ID-103 | Issue draft MVP Integration Spec | 0 | 2021-09-07 | 2021-09-07 | 102 | TRUE |  | Integration | 3 |  |  | Dark Blue (M)
ID-104 | Review/Sign off MVP Integration Spec | 20d | 2021-09-08 | 2021-10-05 | 103 | TRUE |  | Integration | 2 |  | Right | Amber
ID-105 | MVP Data Integration Spec signed off. | 0 | 2021-10-05 | 2021-10-05 | 104 | TRUE |  | Integration | 3 |  | Right | Dark Blue (M)
ID-106 | Integration Technical Design | 50d | 2021-08-11 | 2021-10-19 |  |  |  | Integration | 5 |  |  | Summary Bar
ID-107 | Agree technical delivery approach for England (CLA) | 30d | 2021-08-11 | 2021-09-21 | 79FS +10d | TRUE |  | Integration | 4 |  |  | Amber
ID-108 | Agree technical delivery approach for ScotEID | 40d | 2021-08-25 | 2021-10-19 | 107SS +10d | TRUE |  | Integration | 7 |  |  | Amber
ID-109 | Agree technical delivery approach for EIDCymru to DDTS Integration | 30d | 2021-08-25 | 2021-10-05 | 108SS | TRUE |  | Integration | 8 |  |  | Amber
ID-110 | Agree (common) technical delivery approach for DDTS Integration to UK View | 40d | 2021-08-11 | 2021-10-05 | 107SS | TRUE |  | Integration | 9 |  |  | Amber
ID-111 | Integration Build | 99d | 2021-09-22 | 2022-02-07
ID-112 | England Integration | 80d | 2021-09-22 | 2022-01-11
ID-113 | CLA Build feed to UK View | 60d | 2021-09-22 | 2021-12-14 | 117SS | TRUE |  | Integration | 4 |  |  | Dark Blue
ID-114 | CLA live feed available | 0 | 2021-12-14 | 2021-12-14 | 113 | TRUE |  | Dependencies | 2 |  | Right | Dark Blue (M)
ID-115 | England/Sheep Integration | 80d | 2021-09-22 | 2022-01-11
ID-116 | Build integration from CLA to UK View | 80d | 2021-09-22 | 2022-01-11 | [7 empty] | Summary Bar
ID-117 | Build prototype CLA data integration | 30d | 2021-09-22 | 2021-11-02 | 107 | TRUE |  | Integration | 5 |  | Right | Amber
ID-118 | Re-work CLA data integration when live feed available | 20d | 2021-12-15 | 2022-01-11 | 114 | TRUE |  | Integration | 5 |  | Right | Amber
ID-119 | Integration (England/Sheep) in place | 0 | 2022-01-11 | 2022-01-11 | 118 | TRUE |  | Integration | 6 |  | Right | Dark Blue (M)
ID-120 | England/Cattle Integration | 40d
ID-121 | England/Pig Integration | 40d
ID-122 | Scotland Integration | 50d | 2021-11-30 | 2022-02-07
ID-123 | Scotland/Sheep Integration | 50d | 2021-11-30 | 2022-02-07 | 80 | TRUE |  | Integration | 7 |  |  | Amber
ID-124 | Integration (Scotland/Sheep) in place | 0 | 2022-02-07 | 2022-02-07 | 123 | TRUE |  | Integration | 7 |  | Right | Dark Blue (M)
ID-125 | Scotland/Cattle Integration
ID-126 | Scotland/Pig Integration
ID-127 | Wales Integration | 50d | 2021-10-05 | 2021-12-13
ID-128 | Wales/Sheep Integration | 50d | 2021-10-05 | 2021-12-13 | 81 | TRUE |  | Integration | 8 |  |  | Amber
ID-129 | Integration (Wales/Sheep) in place | 0 | 2021-12-13 | 2021-12-13 | 128 | TRUE |  | Integration | 8 |  | Right | Dark Blue (M)
ID-130 | Wales/Cattle Integration
ID-131 | Wales/Pig Integration
ID-132 | NI Integration
ID-133 | NI/Sheep Integration
ID-134 | NI/Cattle Integration
ID-135 | NI/Pig Integration
ID-136 | UK View Build | 179d | 2021-07-28 | 2022-04-04
ID-137 | Develop backlog for UK View | 20d | 2021-07-28 | 2021-08-24 | 79 | TRUE |  | MVP Build | 1 |  |  | Amber
ID-138 | Manage backlog | 150d | 2021-08-25 | 2022-03-22 | 137 | TRUE |  | MVP Build | 1 |  | Shape | Amber
ID-139 | Develop Infrastructure for UK View | 160d | 2021-08-11 | 2022-03-22 | 138SS -10d | TRUE |  | MVP Build | 2 |  |  | Amber
ID-140 | Validate solution (post England/Sheep Integration) | 10d | 2022-01-12 | 2022-01-25 | 119 | TRUE |  | MVP Build | 3 |  |  | Amber
ID-141 | Validate solution (post Wales/Sheep Integration) | 10d | 2021-12-14 | 2021-12-27 | 129 | TRUE |  | MVP Build | 3 |  |  | Amber
ID-142 | Validate solution (post Scotland/Sheep Integration | 10d | 2022-02-08 | 2022-02-21 | 124 | TRUE |  | MVP Build | 4 |  |  | Amber
ID-143 | Build Solution (Transformation Rules / Database / Reports / Etc) | 140d | 2021-07-28 | 2022-02-08 | 85SS -30d | TRUE |  | MVP Build | 4 |  | Shape | Amber
ID-144 | UAT | 30d | 2022-02-22 | 2022-04-04 | 142 | TRUE |  | MVP Build | 4 |  | Shape | Amber
ID-145 | UK View (MVP) Live | 0 | 2022-04-04 | 2022-04-04 | 144 | TRUE |  | MVP Build | 4 |  | Right | Dark Blue (M)
ID-146 | Demonstrate aggregation capability | 139d | 2021-08-25 | 2022-03-07
ID-147 | Phase 1 Aggregation (white box) | 40d | 2021-08-25 | 2021-10-19 | 137 | TRUE |  | Aggregation | 1 |  |  | Amber
ID-148 | Phase 2a Aggregation (live extract) | 20d | 2021-08-26 | 2021-09-22 | 90 | TRUE |  | Aggregation | 2 |  |  | Amber
ID-149 | Phase 2b Aggregation (live extract) | 20d | 2021-09-23 | 2021-10-20 | 148 | TRUE |  | Aggregation | 2 |  | Right | Amber
ID-150 | Phase 2c Aggregation (live extract) | 20d | 2021-10-21 | 2021-11-17 | 149 | TRUE |  | Aggregation | 3 |  |  | Amber
ID-151 | Phase 3a Aggregation (live integration) | 20d | 2021-12-14 | 2022-01-10 | 129 | TRUE |  | Aggregation | 4 |  |  | Amber
ID-152 | Phase 3b Aggregation (live integration) | 20d | 2022-01-12 | 2022-02-08 | 119 | TRUE |  | Aggregation | 4 |  | Right | Amber
ID-153 | Phase 3b Aggregation (live integration) | 20d | 2022-02-08 | 2022-03-07 | 124 | TRUE |  | Aggregation | 5 |  |  | Amber