## Task_Data
ID | Active | Task Mode | Task_Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names
1 | Yes | Auto Scheduled | FGH D365 Transformation Plan | 573 days? | 10 June 2022 08:00 | 22 August 2024 17:00
2 | Yes | Auto Scheduled | Pre-Requisite | 280 days? | 10 June 2022 08:00 | 06 July 2023 17:00
3 | Yes | Auto Scheduled | Environment | 280 days? | 10 June 2022 08:00 | 06 July 2023 17:00
4 | Yes | Auto Scheduled | Environment Strategy | 1 day? | 10 June 2022 08:00 | 10 June 2022 17:00
5 | Yes | Auto Scheduled | Development Environment | 1 day | 27 June 2022 08:00 | 27 June 2022 17:00 |  | Ananth
6 | Yes | Auto Scheduled | Gold Environment User | 1 day | 28 June 2022 08:00 | 28 June 2022 17:00 | 5 | Ananth
7 | Yes | Auto Scheduled | Demo Environment | 1 day | 28 June 2022 08:00 | 28 June 2022 17:00 | 5 | Ananth
8 | Yes | Auto Scheduled | SIT Environment | 2 days | 27 June 2022 08:00 | 28 June 2022 17:00
9 | Yes | Auto Scheduled | UAT Environment | 1 day | 23 January 2023 08:00 | 23 January 2023 17:00
10 | Yes | Auto Scheduled | Performance Env | 1 day | 07 February 2023 08:00 | 07 February 2023 17:00
11 | Yes | Auto Scheduled | Pre Prod | 1 day | 26 June 2023 08:00 | 26 June 2023 17:00
12 | Yes | Auto Scheduled | Production | 1 day | 06 July 2023 08:00 | 06 July 2023 17:00
13 | Yes | Auto Scheduled | Basic Setup and Configurations : (To be done by Finance Team) | 15 days | 10 June 2022 08:00 | 30 June 2022 17:00
14 | Yes | Auto Scheduled | Legal Entity Creation Inventory and Financial Posting | 2 days | 29 June 2022 08:00 | 30 June 2022 17:00 | 7 | Ananth
15 | Yes | Auto Scheduled | FGH - to validate the config and approve | 1 day | 10 June 2022 08:00 | 10 June 2022 17:00 |  | FGH,Ananth
16 | Yes | Auto Scheduled | Discovery | 306 days | 10 June 2022 08:00 | 11 August 2023 17:00
17 | Yes | Auto Scheduled | Pre work shop questionaire to FGH | 33 days | 27 July 2022 08:00 | 09 September 2022 17:00
18 | Yes | Auto Scheduled | Requirement Detailing | 306 days | 10 June 2022 08:00 | 11 August 2023 17:00
19 | Yes | Auto Scheduled | Requirement Detailing for Product Information Management | 234 days | 20 September 2022 08:00 | 11 August 2023 17:00
20 | Yes | Auto Scheduled | Product Creation discussion with FGH Stocked/Non Stocked and Tracking of Products | 234 days | 20 September 2022 08:00 | 11 August 2023 17:00 |  | Ananth,FGH
21 | Yes | Auto Scheduled | Discussion on Product master data requirement and storage management for all the products(Inbound & Outbound operations) and Unit Conversions | 1 day | 20 September 2022 08:00 | 20 September 2022 17:00
22 | Yes | Auto Scheduled | Product Variants / Product Categories and attributes | 10 days | 21 September 2022 08:00 | 04 October 2022 17:00 | 21
23 | Yes | Auto Scheduled | Requirement document creation for Product Information Management | 13 days | 05 October 2022 08:00 | 21 October 2022 17:00 | 22 | Ananth
24 | Yes | Auto Scheduled | Requirement document feedback | 2 days | 24 October 2022 08:00 | 25 October 2022 17:00 | 23 | FGH
25 | Yes | Auto Scheduled | Requirement document feedback implementation | 15 days | 24 October 2022 08:00 | 11 November 2022 17:00 | 23
26 | Yes | Auto Scheduled | Product Lifecycle - (GEN-997) | 9 days | 30 March 2023 08:00 | 11 April 2023 17:00 |  | Ananth,Maureen Beales
27 | Yes | Auto Scheduled | Meeting 1 | 2 days | 30 March 2023 08:00 | 31 March 2023 17:00 |  | Maureen Beales
28 | Yes | Auto Scheduled | Meeting 2 | 2 days | 30 March 2023 08:00 | 31 March 2023 17:00
29 | Yes | Auto Scheduled | Meeting 3 | 2 days | 30 March 2023 08:00 | 31 March 2023 17:00
30 | Yes | Auto Scheduled | BRD Updated | 2 days | 03 April 2023 08:00 | 04 April 2023 17:00 | 29 | Tech M
31 | Yes | Auto Scheduled | RR updated | 2 days | 10 April 2023 08:00 | 11 April 2023 17:00 |  | Tech M
32 | Yes | Auto Scheduled | EKR meeting (GEN-989) | 19 days | 03 April 2023 08:00 | 27 April 2023 17:00
33 | Yes | Auto Scheduled | Meeting 1 | 1 day | 03 April 2023 08:00 | 03 April 2023 17:00 |  | Maureen Beales
34 | Yes | Auto Scheduled | Meeting 2 | 1 day | 18 April 2023 08:00 | 18 April 2023 17:00 |  | Maureen Beales
35 | Yes | Auto Scheduled | BRD Updated | 1 day | 26 April 2023 08:00 | 26 April 2023 17:00 |  | Tech M
36 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 | 35 | Tech M
37 | Yes | Auto Scheduled | BonPrix Integration Layer (GEN-992) | 16 days | 06 April 2023 08:00 | 27 April 2023 17:00
38 | Yes | Auto Scheduled | Meeting 1 | 1 day | 06 April 2023 08:00 | 06 April 2023 17:00 |  | Maureen Beales
39 | Yes | Auto Scheduled | Meeting 2 | 1 day | 07 April 2023 08:00 | 07 April 2023 17:00 | 38
40 | Yes | Auto Scheduled | BRD Updated | 1 day | 26 April 2023 08:00 | 26 April 2023 17:00 |  | Tech M
41 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 |  | Tech M
42 | Yes | Auto Scheduled | Witt Intergration Layer (GEN-993) | 12 days | 12 April 2023 08:00 | 27 April 2023 17:00
43 | Yes | Auto Scheduled | Meeting 1 | 1 day | 12 April 2023 08:00 | 12 April 2023 17:00 |  | Maureen Beales
44 | Yes | Auto Scheduled | Meeting 2 | 1 day | 13 April 2023 08:00 | 13 April 2023 17:00 | 43
45 | Yes | Auto Scheduled | BRD Updated | 1 day | 26 April 2023 08:00 | 26 April 2023 17:00 |  | Tech M
46 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 |  | Tech M
47 | Yes | Auto Scheduled | DeCapreo (GEN-995) | 18 days | 04 April 2023 08:00 | 27 April 2023 17:00
48 | Yes | Auto Scheduled | Meeting 1 | 1 day | 04 April 2023 08:00 | 04 April 2023 17:00 |  | Maureen Beales
49 | Yes | Auto Scheduled | Meeting 2 | 1 day | 11 April 2023 08:00 | 11 April 2023 17:00 |  | Maureen Beales
50 | Yes | Auto Scheduled | BRD Updated | 1 day | 26 April 2023 08:00 | 26 April 2023 17:00 |  | Ananth
51 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 |  | Ananth
52 | Yes | Auto Scheduled | Common Item Interface (GEN-1221) | 24 days | 11 April 2023 08:00 | 12 May 2023 17:00
53 | Yes | Auto Scheduled | Meeting 1 | 1 day | 11 April 2023 08:00 | 11 April 2023 17:00 |  | Maureen Beales
54 | Yes | Auto Scheduled | Meeting 2 | 1 day | 10 May 2023 08:00 | 10 May 2023 17:00 |  | Maureen Beales,David Thompson,Thomas Gaylard,Steve Lam,Steve Newhouse,John Price,John Wilson
55 | Yes | Auto Scheduled | BRD Updated | 1 day | 11 May 2023 08:00 | 11 May 2023 17:00 | 54 | Ananth
56 | Yes | Auto Scheduled | RR Updated | 1 day | 12 May 2023 08:00 | 12 May 2023 17:00 | 55 | Ananth
57 | Yes | Auto Scheduled | L2C (GEN-1222) | 22 days | 13 April 2023 08:00 | 12 May 2023 17:00
58 | Yes | Auto Scheduled | Meeting 1 | 1 day | 13 April 2023 08:00 | 13 April 2023 17:00 |  | Steve Newhouse,Andrew Russell,David Thompson,Thomas Gaylard,Steve Lam
59 | Yes | Auto Scheduled | Meeting 2 | 1 day | 10 May 2023 08:00 | 10 May 2023 17:00
60 | Yes | Auto Scheduled | BRD Updated | 1 day | 11 May 2023 08:00 | 11 May 2023 17:00 |  | Tech M
61 | Yes | Auto Scheduled | RR Updated | 1 day | 12 May 2023 08:00 | 12 May 2023 17:00 |  | Tech M
62 | Yes | Auto Scheduled | FGH L2C | 4 days | 13 April 2023 08:00 | 18 April 2023 17:00
63 | Yes | Auto Scheduled | Meeting 1 | 8 hrs | 13 April 2023 08:00 | 13 April 2023 17:00
64 | Yes | Auto Scheduled | BRD Updated | 2 days | 14 April 2023 08:00 | 17 April 2023 17:00 | 63 | Tech M
65 | Yes | Auto Scheduled | RR Updated | 1 day | 18 April 2023 08:00 | 18 April 2023 17:00 | 64 | Tech M
66 | Yes | Auto Scheduled | Witt Customer Order Processing | 3 days | 11 April 2023 08:00 | 13 April 2023 17:00
67 | Yes | Auto Scheduled | Meeting 1 | 3 days | 11 April 2023 08:00 | 13 April 2023 17:00
68 | Yes | Auto Scheduled | BRD Updated | 1 day | 12 April 2023 08:00 | 12 April 2023 17:00 |  | Tech M
69 | Yes | Auto Scheduled | RR Updated | 1 day | 13 April 2023 08:00 | 13 April 2023 17:00 | 68 | Tech M
70 | Yes | Auto Scheduled | MDDW (GEN-1225) | 10 days | 14 April 2023 08:00 | 27 April 2023 17:00
71 | Yes | Auto Scheduled | Meeting 1 | 1 day | 14 April 2023 08:00 | 14 April 2023 17:00 | 69
72 | Yes | Auto Scheduled | Meeting 2 | 3 days | 17 April 2023 08:00 | 19 April 2023 17:00 | 71
73 | Yes | Auto Scheduled | Meeting 3 | 1 day | 20 April 2023 08:00 | 20 April 2023 17:00 | 72
74 | Yes | Auto Scheduled | BRD Updated | 4 days | 21 April 2023 08:00 | 26 April 2023 17:00 | 73 | Tech M
75 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 | 74 | Tech M
76 | Yes | Auto Scheduled | MPOS (common order) (GEN-1278) | 3 days | 11 May 2023 08:00 | 15 May 2023 17:00 |  | David Thompson,Steve Lam,Thomas Gaylard,Maureen Beales,Ananth
77 | Yes | Auto Scheduled | Meeting 1 | 1 day | 11 May 2023 08:00 | 11 May 2023 17:00 |  | Andrew Smith,Shaun Guy,Ananth,Arbind,David Thompson,Thomas Gaylard,Steve Lam,Maureen Beales
78 | Yes | Auto Scheduled | BRD Updated | 1 day | 15 May 2023 08:00 | 15 May 2023 17:00 |  | Tech M
79 | Yes | Auto Scheduled | RR Updated | 1 day | 15 May 2023 08:00 | 15 May 2023 17:00 |  | Tech M
80 | Yes | Auto Scheduled | Delivery Promises (GEN-1118) | 22 days | 17 April 2023 08:00 | 16 May 2023 17:00
81 | Yes | Auto Scheduled | Meeting 1 | 1 hr | 17 April 2023 08:00 | 17 April 2023 09:00 |  | Maureen Beales
82 | Yes | Auto Scheduled | Meeting 2 | 1 hr | 09 May 2023 08:00 | 09 May 2023 09:00
83 | Yes | Auto Scheduled | Meeting 3 | 2 hrs | 15 May 2023 08:00 | 15 May 2023 10:00
84 | Yes | Auto Scheduled | BRD Updated | 1 day | 16 May 2023 08:00 | 16 May 2023 17:00
85 | Yes | Auto Scheduled | RR Updated | 1 day | 16 May 2023 08:00 | 16 May 2023 17:00
86 | Yes | Auto Scheduled | Henson (Gen-1064) | 45 days | 21 March 2023 08:00 | 22 May 2023 17:00 |  | Ananth
87 | Yes | Auto Scheduled | Meeting 1 | 6 days | 21 March 2023 08:00 | 28 March 2023 17:00 |  | Maureen Beales,tech M,Ananth,David Thompson
88 | Yes | Auto Scheduled | Meeting 2 | 5 days | 24 April 2023 08:00 | 28 April 2023 17:00 |  | Maureen Beales,tech M,Ananth,David Thompson
89 | Yes | Auto Scheduled | Analysis | 8 days | 01 May 2023 08:00 | 10 May 2023 17:00 | 88
90 | Yes | Auto Scheduled | BRD Updated | 3 days | 11 May 2023 08:00 | 15 May 2023 17:00 | 89 | Ananth
91 | Yes | Auto Scheduled | RR Updated | 3 days | 16 May 2023 08:00 | 18 May 2023 17:00 | 90 | Ananth
92 | Yes | Auto Scheduled | Solution Option Paper | 1 day | 22 May 2023 08:00 | 22 May 2023 17:00
93 | Yes | Auto Scheduled | Split System (GEN-1119) | 6 days | 20 April 2023 08:00 | 27 April 2023 17:00 |  | Ananth
94 | Yes | Auto Scheduled | Meeting 1 | 1 day | 20 April 2023 08:00 | 20 April 2023 17:00 |  | Maureen Beales
95 | Yes | Auto Scheduled | BRD Updated | 1 day | 26 April 2023 08:00 | 26 April 2023 17:00
96 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 | 95
97 | Yes | Auto Scheduled | IV Invoicing | 6 days | 20 April 2023 08:00 | 27 April 2023 17:00
98 | Yes | Auto Scheduled | Meeting 1 | 1 day | 20 April 2023 08:00 | 20 April 2023 17:00
99 | Yes | Auto Scheduled | BRD Updated | 1 day | 26 April 2023 08:00 | 26 April 2023 17:00
100 | Yes | Auto Scheduled | RR Updated | 1 day | 27 April 2023 08:00 | 27 April 2023 17:00 | 99
101 | Yes | Auto Scheduled | Commercial Invoicing | 17 days | 10 May 2023 08:00 | 01 June 2023 17:00
102 | Yes | Auto Scheduled | Meeting 1 | 1 day | 10 May 2023 08:00 | 10 May 2023 17:00 |  | Henning,Shaun Guy,Andrew Smith,David Thompson,Thomas Gaylard,Steve Lam,Maureen Beales,Chat,Lee Schofield
103 | Yes | Auto Scheduled | Meeting 2 | 2 days | 11 May 2023 08:00 | 12 May 2023 17:00 | 102
104 | Yes | Auto Scheduled | BRD Updated | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00
105 | Yes | Auto Scheduled | RR Updated | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00
106 | Yes | Auto Scheduled | Costing | 15 days | 19 July 2023 08:00 | 08 August 2023 17:00
107 | Yes | Auto Scheduled | Meeting 1 | 1 day | 19 July 2023 08:00 | 19 July 2023 17:00 |  | Maureen Beales
108 | Yes | Auto Scheduled | Meeting 2 | 1 day | 01 August 2023 08:00 | 01 August 2023 17:00
109 | Yes | Auto Scheduled | BRD Updated | 1 day | 08 August 2023 08:00 | 08 August 2023 17:00
110 | Yes | Auto Scheduled | RR Updated | 1 day | 08 August 2023 08:00 | 08 August 2023 17:00
111 | Yes | Auto Scheduled | Self Billing (DDTRACK+) (gen-1128) | 2 days | 31 May 2023 08:00 | 01 June 2023 17:00
112 | Yes | Auto Scheduled | Meeting 1 | 1 day | 31 May 2023 08:00 | 31 May 2023 17:00
113 | Yes | Auto Scheduled | BRD Updated | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00
114 | Yes | Auto Scheduled | RR Updated | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00
115 | Yes | Auto Scheduled | 3PL (DDTRACK+) | 2 days | 31 May 2023 08:00 | 01 June 2023 17:00
116 | Yes | Auto Scheduled | Meeting 1 | 1 day | 31 May 2023 08:00 | 31 May 2023 17:00
117 | Yes | Auto Scheduled | BRD Updated | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00
118 | Yes | Auto Scheduled | RR Updated | 1 day | 01 June 2023 08:00 | 01 June 2023 17:00
119 | Yes | Auto Scheduled | Parcel Tracking (GEN-1226) | 34 days | 14 April 2023 08:00 | 31 May 2023 17:00
120 | Yes | Auto Scheduled | Session 1 (including WMS) | 10 days | 14 April 2023 08:00 | 27 April 2023 17:00
121 | Yes | Auto Scheduled | IIB | 2 days | 14 April 2023 08:00 | 17 April 2023 17:00
122 | Yes | Auto Scheduled | Parcel Tracking | 2 days | 18 April 2023 08:00 | 19 April 2023 17:00 | 121
123 | Yes | Auto Scheduled | Arrow XL | 2 days | 20 April 2023 08:00 | 21 April 2023 17:00 | 122
124 | Yes | Auto Scheduled | Parcel Force Consignments | 2 days | 24 April 2023 08:00 | 25 April 2023 17:00 | 123
125 | Yes | Auto Scheduled | Pareclforce Tracking | 2 days | 26 April 2023 08:00 | 27 April 2023 17:00 | 124
126 | Yes | Auto Scheduled | Session 2 | 20 days | 04 May 2023 08:00 | 31 May 2023 17:00
127 | Yes | Auto Scheduled | Hermes Tracking | 1 day | 04 May 2023 08:00 | 04 May 2023 17:00
128 | Yes | Auto Scheduled | Hermes Tracking API | 1 day | 04 May 2023 08:00 | 04 May 2023 17:00
129 | Yes | Auto Scheduled | Stock Balance Cache | 1 day | 04 May 2023 08:00 | 04 May 2023 17:00
130 | Yes | Auto Scheduled | Hermes World | 1 day | 04 May 2023 08:00 | 04 May 2023 17:00
131 | Yes | Auto Scheduled | BRD Updated | 1 day | 31 May 2023 08:00 | 31 May 2023 17:00
132 | Yes | Auto Scheduled | RR Updated | 1 day | 31 May 2023 08:00 | 31 May 2023 17:00
133 | Yes | Auto Scheduled | Imports/Langdons | 7 days | 25 April 2023 08:00 | 03 May 2023 17:00
134 | Yes | Auto Scheduled | Meeting 1 | 1 day | 25 April 2023 08:00 | 25 April 2023 17:00
135 | Yes | Auto Scheduled | Meeting 2 | 1 day | 25 April 2023 08:00 | 25 April 2023 17:00
136 | Yes | Auto Scheduled | BRD Updated | 1 day | 03 May 2023 08:00 | 03 May 2023 17:00
137 | Yes | Auto Scheduled | RR Updated | 1 day | 03 May 2023 08:00 | 03 May 2023 17:00
138 | Yes | Auto Scheduled | Common Tracking | 16 days | 10 May 2023 08:00 | 31 May 2023 17:00
139 | Yes | Auto Scheduled | Meeting 1 | 1 day | 10 May 2023 08:00 | 10 May 2023 17:00 |  | Maureen Beales
140 | Yes | Auto Scheduled | BRD Updated | 1 day | 31 May 2023 08:00 | 31 May 2023 17:00
141 | Yes | Auto Scheduled | RR Updated | 1 day | 31 May 2023 08:00 | 31 May 2023 17:00
142 | Yes | Auto Scheduled | Stock Balances (GEN-1223) | 4 days | 03 April 2023 08:00 | 06 April 2023 17:00
143 | Yes | Auto Scheduled | Meetings 1 | 1 day | 03 April 2023 08:00 | 03 April 2023 17:00
144 | Yes | Auto Scheduled | Meeting | 1 day | 04 April 2023 08:00 | 04 April 2023 17:00 | 143
145 | Yes | Auto Scheduled | BRD Updated | 1 day | 06 April 2023 08:00 | 06 April 2023 17:00
146 | Yes | Auto Scheduled | RR Updated | 1 day | 06 April 2023 08:00 | 06 April 2023 17:00
147 | Yes | Auto Scheduled | DDtrack & DDtrack+ (GEN-1219) | 8 days | 27 April 2023 08:00 | 08 May 2023 17:00
148 | Yes | Auto Scheduled | Meeting 1 | 5 days | 27 April 2023 08:00 | 03 May 2023 17:00
149 | Yes | Auto Scheduled | Analysis document | 5 days | 01 May 2023 08:00 | 05 May 2023 17:00
150 | Yes | Auto Scheduled | BRD Updated | 1 day | 08 May 2023 08:00 | 08 May 2023 17:00 | 149
151 | Yes | Auto Scheduled | RR Updated | 1 day | 08 May 2023 08:00 | 08 May 2023 17:00 | 149
152 | Yes | Auto Scheduled | Item Talk (GEN-990) | 2 days | 01 May 2023 08:00 | 02 May 2023 17:00
153 | Yes | Auto Scheduled | Meeting 1 | 1 day | 01 May 2023 08:00 | 01 May 2023 17:00
154 | Yes | Auto Scheduled | Meeting 2 | 1 day | 02 May 2023 08:00 | 02 May 2023 17:00 | 153
155 | Yes | Auto Scheduled | BRD Updated | 1 day | 02 May 2023 08:00 | 02 May 2023 17:00
156 | Yes | Auto Scheduled | RR Updated | 1 day | 02 May 2023 08:00 | 02 May 2023 17:00
157 | Yes | Auto Scheduled | Commodity Codes (GEN-1279) | 11 days | 13 July 2023 08:00 | 27 July 2023 17:00
158 | Yes | Auto Scheduled | Meeting 1 | 1 day | 13 July 2023 08:00 | 13 July 2023 17:00
159 | Yes | Auto Scheduled | Meeting 2 | 1 day | 17 July 2023 08:00 | 17 July 2023 17:00
160 | Yes | Auto Scheduled | BRD Updated | 1 day | 27 July 2023 08:00 | 27 July 2023 17:00 |  | Ananth
161 | Yes | Auto Scheduled | RR Updated | 1 day | 27 July 2023 08:00 | 27 July 2023 17:00 |  | Ananth
162 | Yes | Auto Scheduled | Pimberley | 8 days | 02 August 2023 08:00 | 11 August 2023 17:00
163 | Yes | Auto Scheduled | Meeting 1 | 2 days | 02 August 2023 08:00 | 03 August 2023 17:00 |  | Maureen Beales
164 | Yes | Auto Scheduled | Meeting 2 | 1 day | 04 August 2023 08:00 | 04 August 2023 17:00 | 163 | Maureen Beales
165 | Yes | Auto Scheduled | Analysis Document | 2 days | 07 August 2023 08:00 | 08 August 2023 17:00 | 164
166 | Yes | Auto Scheduled | BRD Updated | 2 days | 09 August 2023 08:00 | 10 August 2023 17:00 | 165 | Ananth
167 | Yes | Auto Scheduled | RR Updated | 1 day | 11 August 2023 08:00 | 11 August 2023 17:00 | 166 | Ananth
168 | Yes | Auto Scheduled | Requirement Detailing for Customer Master | 3 days | 04 November 2022 08:00 | 08 November 2022 17:00
169 | Yes | Auto Scheduled | Relationship Initiation process Identifying Potential Customers, Customer creation process | 3 days | 04 November 2022 08:00 | 08 November 2022 17:00
170 | Yes | Auto Scheduled | Discussion on Customer master data (Different Fields like Categorization of Business, Payment Defaults, Credit rating & limit ..) and Customer Specific MIS Reports | 1 day | 04 November 2022 08:00 | 04 November 2022 17:00
171 | Yes | Auto Scheduled | Customer Master & Sub Master Discussion | 1 day | 07 November 2022 08:00 | 07 November 2022 17:00 | 170
172 | Yes | Auto Scheduled | Requirement Document preparation for Customer Master | 3 days | 04 November 2022 08:00 | 08 November 2022 17:00 | 170SS
173 | Yes | Auto Scheduled | Requirement Detailing for Sales Order Management | 75 days | 01 November 2022 08:00 | 13 February 2023 17:00
174 | Yes | Auto Scheduled | Sales Delivery Management | 30 days | 01 November 2022 08:00 | 06 January 2023 17:00
175 | Yes | Auto Scheduled | Sales Order Sub-Master Discussion | 1 day | 09 January 2023 08:00 | 09 January 2023 17:00 | 174
176 | Yes | Auto Scheduled | Sales categories / Classification groups /Sales Order Pools / Sales Origin / Sales Order Hold Codes | 9 days | 10 January 2023 08:00 | 20 January 2023 17:00 | 175
177 | Yes | Auto Scheduled | Trade Agreements / Sales Agreements (Prices and discounts) | 1 day | 23 January 2023 08:00 | 23 January 2023 17:00 | 176
178 | Yes | Auto Scheduled | Sales Return Process Discussion | 1 day | 23 January 2023 08:00 | 23 January 2023 17:00 | 176
179 | Yes | Auto Scheduled | Requirement document for Sales Order Processing | 14 days | 24 January 2023 08:00 | 10 February 2023 17:00 | 178
180 | Yes | Auto Scheduled | Sales Order Lifecycle - Deliverable Document - Approved | 1 day | 13 February 2023 08:00 | 13 February 2023 17:00 | 179
181 | Yes | Auto Scheduled | Requirement Detailing for Procurement and sourcing | 305 days | 10 June 2022 08:00 | 10 August 2023 17:00
182 | Yes | Auto Scheduled | Procurement and sourcing | 73 days | 17 November 2022 08:00 | 27 February 2023 17:00
183 | Yes | Auto Scheduled | Vendors (Vendor Master) Discussion | 20 days | 17 November 2022 08:00 | 14 December 2022 17:00
184 | Yes | Auto Scheduled | Vendor Master & Sub Master Discussion | 1 day | 15 December 2022 08:00 | 15 December 2022 17:00 | 183
185 | Yes | Auto Scheduled | Purchase Order Management Discussion | 20 days | 16 December 2022 08:00 | 12 January 2023 17:00 | 184
186 | Yes | Auto Scheduled | Purchase Order Sub-Master Discussion | 1 day | 13 January 2023 08:00 | 13 January 2023 17:00 | 185
187 | Yes | Auto Scheduled | Purchase Pools/ Reason / Buyer group | 1 day | 16 January 2023 08:00 | 16 January 2023 17:00 | 186
188 | Yes | Auto Scheduled | Import/Exports - Discussions | 5 days | 17 January 2023 08:00 | 23 January 2023 17:00 | 187
189 | Yes | Auto Scheduled | Costings | 1 day | 24 January 2023 08:00 | 24 January 2023 17:00 | 188
190 | Yes | Auto Scheduled | Purchase Return Process Discussion | 3 days | 25 January 2023 08:00 | 27 January 2023 17:00 | 189
191 | Yes | Auto Scheduled | Requirement document for Procurement and Sourcing | 20 days | 30 January 2023 08:00 | 24 February 2023 17:00 | 190
192 | Yes | Auto Scheduled | Purchase Order Lifecycle - Deliverable Document - Approved | 1 day | 27 February 2023 08:00 | 27 February 2023 17:00 | 191
193 | Yes | Auto Scheduled | Requirement Detailing for Inventory and Financial Posting | 16 days | 10 May 2023 08:00 | 31 May 2023 17:00
194 | Yes | Auto Scheduled | Accounts Payable | 2 days | 10 May 2023 08:00 | 11 May 2023 17:00
195 | Yes | Auto Scheduled | Accounts Receivable | 2 days | 12 May 2023 08:00 | 15 May 2023 17:00 | 194
196 | Yes | Auto Scheduled | Inventory Postings | 2 days | 16 May 2023 08:00 | 17 May 2023 17:00 | 195
197 | Yes | Auto Scheduled | Customs processes/reporting | 10 days | 18 May 2023 08:00 | 31 May 2023 17:00 | 196
198 | Yes | Auto Scheduled | Integration Requirement understanding | 208 days | 10 June 2022 08:00 | 28 March 2023 17:00
199 | Yes | Auto Scheduled | Integration Strategy | 20 days | 10 June 2022 08:00 | 07 July 2022 17:00
200 | Yes | Auto Scheduled | Integration with WMS | 10 days | 16 February 2023 08:00 | 01 March 2023 17:00 |  | FGH/Tech M
201 | Yes | Auto Scheduled | Integration with E-Commerce | 10 days | 02 March 2023 08:00 | 15 March 2023 17:00 | 200 | FGH/Tech M
202 | Yes | Auto Scheduled | Integration with CRM | 1 day | 16 March 2023 08:00 | 16 March 2023 17:00 | 201 | FGH/Tech M
203 | Yes | Auto Scheduled | Other integrations | 8 days | 17 March 2023 08:00 | 28 March 2023 17:00 | 202 | FGH/Tech M
204 | Yes | Auto Scheduled | Cross tower Requirements | 28 days | 04 July 2023 08:00 | 10 August 2023 17:00
205 | Yes | Auto Scheduled | Import export | 5 days | 04 July 2023 08:00 | 10 July 2023 17:00
206 | Yes | Auto Scheduled | Costing s | 1 day | 01 August 2023 08:00 | 01 August 2023 17:00
207 | Yes | Auto Scheduled | Purschase return discussion | 1 day | 02 August 2023 08:00 | 02 August 2023 17:00 | 206
208 | Yes | Auto Scheduled | BRD Updated | 5 days | 03 August 2023 08:00 | 09 August 2023 17:00 | 207
209 | Yes | Auto Scheduled | RR Updated | 1 day | 10 August 2023 08:00 | 10 August 2023 17:00 | 208
210 | Yes | Auto Scheduled | Business Proceeds Sign-Off | 306 days | 10 June 2022 08:00 | 11 August 2023 17:00
211 | Yes | Auto Scheduled | Requirements Register | 306 days | 10 June 2022 08:00 | 11 August 2023 17:00
212 | Yes | Auto Scheduled | FIT-GAP Analysis for SCM Modules | 78 days | 10 June 2022 08:00 | 27 September 2022 17:00 |  | Tech M
213 | Yes | Auto Scheduled | Business Requirement Document sign of | 66 days | 12 May 2023 08:00 | 11 August 2023 17:00 |  | FGH
214 | Yes | Auto Scheduled | Draft | 1 day | 12 May 2023 08:00 | 12 May 2023 17:00 |  | FGH
215 | Yes | Auto Scheduled | FGH Review | 56 days | 15 May 2023 08:00 | 31 July 2023 17:00 | 214 | FGH
216 | Yes | Auto Scheduled | Approval and Sign off | 9 days | 01 August 2023 08:00 | 11 August 2023 17:00 | 215 | FGH
217 | Yes | Auto Scheduled | Requirement Register | 66 days | 12 May 2023 08:00 | 11 August 2023 17:00 |  | FGH
218 | Yes | Auto Scheduled | Draft | 1 day | 12 May 2023 08:00 | 12 May 2023 17:00 |  | FGH
219 | Yes | Auto Scheduled | FGH Review | 56 days | 15 May 2023 08:00 | 31 July 2023 17:00 | 218 | FGH
220 | Yes | Auto Scheduled | Approval and Sign off | 9 days | 01 August 2023 08:00 | 11 August 2023 17:00 | 219
221 | Yes | Auto Scheduled | Design and Configure | 99 days | 14 August 2023 08:00 | 01 January 2024 17:00
222 | Yes | Auto Scheduled | SBR Documentation for SCM | 26 days | 03 October 2023 08:00 | 07 November 2023 17:00
223 | Yes | Auto Scheduled | Preparation | 20 days | 03 October 2023 08:00 | 30 October 2023 17:00
224 | Yes | Auto Scheduled | walkthrough | 1 day | 31 October 2023 08:00 | 31 October 2023 17:00 | 223
225 | Yes | Auto Scheduled | feedbback and updates | 5 days | 01 November 2023 08:00 | 07 November 2023 17:00 | 224
226 | Yes | Auto Scheduled | Functional Design Document (FDD) | 99 days | 14 August 2023 08:00 | 01 January 2024 17:00
227 | Yes | Auto Scheduled | Functional Design Document preparation for Gaps, Integrations and Customizations | 99 days | 14 August 2023 08:00 | 01 January 2024 17:00 |  | Tech M
228 | Yes | Auto Scheduled | Functional Design document preparation ( Based on customization )- Submit | 80 days | 14 August 2023 08:00 | 04 December 2023 17:00 | 220 | Tech M
229 | Yes | Auto Scheduled | Feedback from FGH on Functional design document | 85 days | 22 August 2023 08:00 | 18 December 2023 17:00 | 228SS+5d | FGH
230 | Yes | Auto Scheduled | Functional Design document - Update feedback document & Submit | 90 days | 25 August 2023 08:00 | 29 December 2023 17:00 | 229SS+3d | Tech M
231 | Yes | Auto Scheduled | Functional Design document Sign off | 1 day | 01 January 2024 08:00 | 01 January 2024 17:00 | 230 | FGH
232 | Yes | Auto Scheduled | Configuration Activities | 48 days | 21 August 2023 08:00 | 25 October 2023 17:00
233 | Yes | Auto Scheduled | Setup and Configurations Product Information Management | 14 days | 21 August 2023 08:00 | 07 September 2023 17:00
234 | Yes | Auto Scheduled | Storage Dimensions:- Site Master / Warehouse Master | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
235 | Yes | Auto Scheduled | Tracking Dimension Details:- Batch Sequence / Serial Sequence | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
236 | Yes | Auto Scheduled | Product Dimension Details:- Style / Size / Color | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
237 | Yes | Auto Scheduled | Product Categories and Attributes :-Category hierarchies | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
238 | Yes | Auto Scheduled | Attribute types / Attributes / Attribute groups | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
239 | Yes | Auto Scheduled | Batch attributes / Batch attribute groups | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
240 | Yes | Auto Scheduled | Item Group | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
241 | Yes | Auto Scheduled | Item Model Group | 10 days | 21 August 2023 08:00 | 01 September 2023 17:00 |  | Tech M
242 | Yes | Auto Scheduled | Product Life Cycle | 4 days | 04 September 2023 08:00 | 07 September 2023 17:00 |  | Tech M
243 | Yes | Auto Scheduled | Sales Tax Group | 3 days | 04 September 2023 08:00 | 06 September 2023 17:00 |  | Tech M
244 | Yes | Auto Scheduled | Units and Unit Conversions | 3 days | 04 September 2023 08:00 | 06 September 2023 17:00 |  | Tech M
245 | Yes | Auto Scheduled | No. Sequence Configuration | 3 days | 04 September 2023 08:00 | 06 September 2023 17:00 |  | Tech M
246 | Yes | Auto Scheduled | FGH Specific Standard Product Setup and Configurations based on the Sample Data | 3 days | 04 September 2023 08:00 | 06 September 2023 17:00 |  | Tech M
247 | Yes | Auto Scheduled | Setup and Configurations Inventory Management | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00
248 | Yes | Auto Scheduled | FGH Specific Standard Inventory Management Setup and Configurations | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
249 | Yes | Auto Scheduled | Inventory blocking | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
250 | Yes | Auto Scheduled | ABC classification | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
251 | Yes | Auto Scheduled | Ship transfer order / Receive transfer order | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
252 | Yes | Auto Scheduled | Inventory Journals | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
253 | Yes | Auto Scheduled | Items Movement / Items Inventory adjustment / Items Transfer / Item Counting Journal | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
254 | Yes | Auto Scheduled | Inventory Management Parameters and Workflows | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
255 | Yes | Auto Scheduled | FGH Specific Standard Inventory Management Setup and Configurations | 5 days | 11 September 2023 08:00 | 15 September 2023 17:00 |  | Tech M
256 | Yes | Auto Scheduled | Setup and Configurations Customer Master (Main data in CRM) | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00
257 | Yes | Auto Scheduled | Customer Group / Customer Default Sites / Warehouse | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00 |  | Tech M
258 | Yes | Auto Scheduled | Currencies / Customer Method of Payment / Payment Schedule | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00 |  | Tech M
259 | Yes | Auto Scheduled | Mode of Delivery /Terms of Delivery/Terms of Payment | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00 |  | Tech M
260 | Yes | Auto Scheduled | Sales Tax Group /With holding tax | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00 |  | Tech M
261 | Yes | Auto Scheduled | No. Sequence Configuration | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00 |  | Tech M
262 | Yes | Auto Scheduled | FGH Specific Standard Customer Setup and Configurations based on the Sample Data | 2 days | 18 September 2023 08:00 | 19 September 2023 17:00 |  | Tech M
263 | Yes | Auto Scheduled | Setup and Configurations Sales Order Management | 12 days | 21 September 2023 08:00 | 06 October 2023 17:00
264 | Yes | Auto Scheduled | No. Sequence Configuration | 1 day | 21 September 2023 08:00 | 21 September 2023 17:00 |  | Tech M
265 | Yes | Auto Scheduled | Sales and Marketing Parameters and Workflows | 3 days | 22 September 2023 08:00 | 26 September 2023 17:00 |  | Tech M
266 | Yes | Auto Scheduled | Sales and Marketing FGH Specific Standard Setup and Configurations | 3 days | 22 September 2023 08:00 | 26 September 2023 17:00 |  | Tech M
267 | Yes | Auto Scheduled | Delivery Management (Delivery Note) / Customer Delivery address | 1 day | 03 October 2023 08:00 | 03 October 2023 17:00 |  | Tech M
268 | Yes | Auto Scheduled | Delivery date control / Over delivery / Under delivery | 1 day | 03 October 2023 08:00 | 03 October 2023 17:00 |  | Tech M
269 | Yes | Auto Scheduled | Reservation Management / Pick List Generation / Registration / Packing Slip | 1 day | 03 October 2023 08:00 | 03 October 2023 17:00 |  | Tech M
270 | Yes | Auto Scheduled | Sales Return Setups Configurations Disposition codes / Return reason code groups / Return reason codes | 3 days | 04 October 2023 08:00 | 06 October 2023 17:00 |  | Tech M
271 | Yes | Auto Scheduled | Setup and Configurations for Vendor Master and Procurement and sourcing | 7 days | 09 October 2023 08:00 | 17 October 2023 17:00
272 | Yes | Auto Scheduled | Vendor Specific Setup and Configurations | 1 day | 09 October 2023 08:00 | 09 October 2023 17:00 |  | Tech M
273 | Yes | Auto Scheduled | Purchasing policies / Invoice Matching Policies | 1 day | 09 October 2023 08:00 | 09 October 2023 17:00 |  | Tech M
274 | Yes | Auto Scheduled | Vendor Group / Default Sites / Warehouse | 1 day | 10 October 2023 08:00 | 10 October 2023 17:00 |  | Tech M
275 | Yes | Auto Scheduled | Currencies / Vendor Method of Payment / Payment Schedule | 1 day | 10 October 2023 08:00 | 10 October 2023 17:00 |  | Tech M
276 | Yes | Auto Scheduled | Mode of Delivery /Terms of Delivery/Terms of Payment | 1 day | 11 October 2023 08:00 | 11 October 2023 17:00 |  | Tech M
277 | Yes | Auto Scheduled | Sales Tax Group /With holding tax | 1 day | 11 October 2023 08:00 | 11 October 2023 17:00 |  | Tech M
278 | Yes | Auto Scheduled | No. Sequence Configuration | 1 day | 12 October 2023 08:00 | 12 October 2023 17:00 |  | Tech M
279 | Yes | Auto Scheduled | Procurement and sourcing parameters and Workflows | 1 day | 12 October 2023 08:00 | 12 October 2023 17:00 |  | Tech M
280 | Yes | Auto Scheduled | Procurement and sourcing FGH Specific Standard Setup and Configurations | 1 day | 16 October 2023 08:00 | 16 October 2023 17:00 |  | Tech M
281 | Yes | Auto Scheduled | Purchase Return Setups Configurations | 1 day | 17 October 2023 08:00 | 17 October 2023 17:00 |  | Tech M
282 | Yes | Auto Scheduled | Setup and Configurations for Physical and Financial Postings | 6 days | 18 October 2023 08:00 | 25 October 2023 17:00
283 | Yes | Auto Scheduled | Inventory and Financial Posting Setup and Configuration / Pick and Packing | 3 days | 18 October 2023 08:00 | 20 October 2023 17:00 |  | Tech M
284 | Yes | Auto Scheduled | Sales Postings /Delivery Postings /Invoice Postings /Customer Postings | 2 days | 23 October 2023 08:00 | 24 October 2023 17:00 |  | Tech M
285 | Yes | Auto Scheduled | Purchase Postings /GRN postings /Invoice postings / Vendor postings | 2 days | 24 October 2023 08:00 | 25 October 2023 17:00 |  | Tech M
286 | Yes | Auto Scheduled | Build and Test | 121 days | 11 September 2023 08:00 | 27 February 2024 17:00
287 | Yes | Auto Scheduled | Development based on Gaps and Customizations | 121 days | 11 September 2023 08:00 | 27 February 2024 17:00 |  | Tech M
288 | Yes | Auto Scheduled | Gaps and Customization implementation | 40 days | 11 September 2023 08:00 | 03 November 2023 17:00
289 | Yes | Auto Scheduled | Development related to integration with WMS, Ecommerce, CRM, Pimberly, Ratalon and other Modules | 90 days | 17 October 2023 08:00 | 20 February 2024 17:00 |  | Tech M
290 | Yes | Auto Scheduled | Sanity and Unit testing for integrations | 85 days | 31 October 2023 08:00 | 27 February 2024 17:00 |  | Tech M
291 | Yes | Auto Scheduled | System Integration and testing (SIT) | 124 days | 25 September 2023 08:00 | 15 March 2024 17:00
292 | Yes | Auto Scheduled | Test Cases creation | 103 days | 25 September 2023 08:00 | 15 February 2024 17:00 |  | Tech M
293 | Yes | Auto Scheduled | Product Master Creation | 5 days | 25 September 2023 08:00 | 29 September 2023 17:00 |  | Tech M
294 | Yes | Auto Scheduled | Customer Master Creation | 2 days | 02 October 2023 08:00 | 03 October 2023 17:00 | 293 | Tech M
295 | Yes | Auto Scheduled | Sales Order Testing / Delivery Note Generation / Outbound Process | 10 days | 04 October 2023 08:00 | 17 October 2023 17:00 | 294 | Tech M
296 | Yes | Auto Scheduled | Sale Return Process Testing | 3 days | 18 October 2023 08:00 | 20 October 2023 17:00 | 295 | Tech M
297 | Yes | Auto Scheduled | Vendor Master Creation | 5 days | 23 October 2023 08:00 | 27 October 2023 17:00 | 296 | Tech M
298 | Yes | Auto Scheduled | Trade Agreements / Sales Agreements Creation | 5 days | 30 October 2023 08:00 | 03 November 2023 17:00 | 297 | Tech M
299 | Yes | Auto Scheduled | Purchase Order Testing / Good Receipt Note / Inbound Process | 5 days | 06 November 2023 08:00 | 10 November 2023 17:00 | 298 | Tech M
300 | Yes | Auto Scheduled | Purchase Return Process Testing | 2 days | 02 October 2023 08:00 | 03 October 2023 17:00 | 293 | Tech M
301 | Yes | Auto Scheduled | Packing Slip Posting / Invoice posting / Customer Profile Posting | 3 days | 04 October 2023 08:00 | 06 October 2023 17:00 | 294 | Tech M
302 | Yes | Auto Scheduled | GRN Posting /Vendor Invoice posting /Vendor Profile Posting | 3 days | 18 October 2023 08:00 | 20 October 2023 17:00 | 295 | Tech M
303 | Yes | Auto Scheduled | Import/Export - Commercial Invoicing | 5 days | 23 October 2023 08:00 | 27 October 2023 17:00 | 296 | Tech M
304 | Yes | Auto Scheduled | Integration testing for WMS | 45 days | 23 October 2023 08:00 | 22 December 2023 17:00 | 296 | Tech M
305 | Yes | Auto Scheduled | Integration testing for E-Commerce | 45 days | 23 October 2023 08:00 | 22 December 2023 17:00 | 296 | Tech M
306 | Yes | Auto Scheduled | Integration testing for CRM | 45 days | 23 October 2023 08:00 | 22 December 2023 17:00 | 296 | Tech M
307 | Yes | Auto Scheduled | Integration testing with Other systems | 60 days | 23 October 2023 08:00 | 15 January 2024 17:00 | 296 | Tech M
308 | Yes | Auto Scheduled | Test Cases review | 100 days | 27 September 2023 08:00 | 14 February 2024 17:00 | 293SS+2d | Tech M
309 | Yes | Auto Scheduled | Test Cases - submitt/sgn off | 1 day | 15 February 2024 08:00 | 15 February 2024 17:00 | 308 | Tech M
310 | Yes | Auto Scheduled | SIT testing | 99 days | 30 October 2023 08:00 | 15 March 2024 17:00
311 | Yes | Auto Scheduled | Configuration and code deployment | 50 days | 30 October 2023 08:00 | 08 January 2024 17:00 | 303
312 | Yes | Auto Scheduled | Testing | 50 days | 01 November 2023 08:00 | 10 January 2024 17:00 | 311SS+2d
313 | Yes | Auto Scheduled | Gaps and Customization implementation | 15 days | 12 February 2024 08:00 | 01 March 2024 17:00 | 312SS+1d | Tech M
314 | Yes | Auto Scheduled | Development related to integration with WMS, Ecommerce, CRM, Pimberly, Ratalon and other Modules | 2 days | 28 February 2024 08:00 | 29 February 2024 17:00 | 290 | Tech M
315 | Yes | Auto Scheduled | Testing feedback and code/configuraiton updated | 10 days | 01 March 2024 08:00 | 14 March 2024 17:00 | 314
316 | Yes | Auto Scheduled | Testing sign off | 1 day | 15 March 2024 08:00 | 15 March 2024 17:00 | 315
317 | Yes | Auto Scheduled | End to End testing | 39 days? | 16 January 2023 08:00 | 09 March 2023 17:00
318 | Yes | Auto Scheduled | Tes case preparation | 15 days | 16 January 2023 08:00 | 03 February 2023 17:00
319 | Yes | Auto Scheduled | Test case validation | 15 days | 17 January 2023 08:00 | 06 February 2023 17:00 | 318SS+1d
320 | Yes | Auto Scheduled | Test case execution | 20 days | 07 February 2023 08:00 | 06 March 2023 17:00 | 319
321 | Yes | Auto Scheduled | Test case feedback and updates | 20 days | 09 February 2023 08:00 | 08 March 2023 17:00 | 320SS+2d
322 | Yes | Auto Scheduled | E2E sign off | 1 day? | 09 March 2023 08:00 | 09 March 2023 17:00 | 321
323 | Yes | Auto Scheduled | Data Migration | 63 days | 04 September 2023 08:00 | 29 November 2023 17:00
324 | Yes | Auto Scheduled | Data Migration Strategy | 10 days | 18 September 2023 08:00 | 29 September 2023 17:00
325 | Yes | Auto Scheduled | Draft | 7 days | 18 September 2023 08:00 | 26 September 2023 17:00 |  | Tech M
326 | Yes | Auto Scheduled | Review | 2 days | 27 September 2023 08:00 | 28 September 2023 17:00 | 325 | FGH
327 | Yes | Auto Scheduled | Approve/Sign off | 1 day | 29 September 2023 08:00 | 29 September 2023 17:00 | 326 | FGH
328 | Yes | Auto Scheduled | SBR implementation work shop | 7 days | 02 October 2023 08:00 | 10 October 2023 17:00
329 | Yes | Auto Scheduled | Preparation | 4 days | 02 October 2023 08:00 | 05 October 2023 17:00 |  | Tech M
330 | Yes | Auto Scheduled | walkthrough | 1 day | 06 October 2023 08:00 | 06 October 2023 17:00 | 329 | Tech M,MS
331 | Yes | Auto Scheduled | feedbback and updates | 2 days | 09 October 2023 08:00 | 10 October 2023 17:00 | 330 | MS,Tech M
332 | Yes | Auto Scheduled | Product Master Template Discussion | 30 days | 04 September 2023 08:00 | 13 October 2023 17:00
333 | Yes | Auto Scheduled | All Product Master and sub-Master Data from FGH | 20 days | 04 September 2023 08:00 | 29 September 2023 17:00 |  | FGH
334 | Yes | Auto Scheduled | Import of Product Master and Sub-Master data of FGH | 20 days | 11 September 2023 08:00 | 06 October 2023 17:00 |  | Tech M
335 | Yes | Auto Scheduled | All received Product Master & Sub-Master Validation | 5 days | 02 October 2023 08:00 | 06 October 2023 17:00 |  | FGH,Tech M
336 | Yes | Auto Scheduled | Confirmation of Imported Product data into ERP | 5 days | 09 October 2023 08:00 | 13 October 2023 17:00 |  | FGH,Tech M
337 | Yes | Auto Scheduled | Customer Master Template Discussion | 37 days | 18 September 2023 08:00 | 07 November 2023 17:00
338 | Yes | Auto Scheduled | All Customer Master and sub-Master Data from FGH | 20 days | 18 September 2023 08:00 | 13 October 2023 17:00 |  | FGH
339 | Yes | Auto Scheduled | Import of Customer Master and Sub-Master data of FGH | 20 days | 25 September 2023 08:00 | 20 October 2023 17:00 |  | Tech M
340 | Yes | Auto Scheduled | All received Customer Master & Sub-Master Validation | 5 days | 23 October 2023 08:00 | 27 October 2023 17:00 |  | FGH,Tech M
341 | Yes | Auto Scheduled | FGH Sales Order Sub-Master | 20 days | 02 October 2023 08:00 | 27 October 2023 17:00 |  | FGH,Tech M
342 | Yes | Auto Scheduled | Confirmation of Imported Customer data into ERP | 7 days | 30 October 2023 08:00 | 07 November 2023 17:00 |  | FGH,Tech M
343 | Yes | Auto Scheduled | Vendor Master Template Discussion | 43 days | 02 October 2023 08:00 | 29 November 2023 17:00
344 | Yes | Auto Scheduled | All Vendor Master and sub-Master Data from FGH | 20 days | 02 October 2023 08:00 | 27 October 2023 17:00 |  | FGH
345 | Yes | Auto Scheduled | Import of Vendor Master and Sub-Master data of FGH | 20 days | 05 October 2023 08:00 | 01 November 2023 17:00 |  | Tech M
346 | Yes | Auto Scheduled | All received Vendor Master & Sub-Master Validation | 7 days | 09 October 2023 08:00 | 17 October 2023 17:00 |  | FGH,Tech M
347 | Yes | Auto Scheduled | FGH Purchase Order Sub-Master (including import & Export) | 25 days | 17 October 2023 08:00 | 20 November 2023 17:00 |  | FGH,Tech M
348 | Yes | Auto Scheduled | Confirmation of Imported Vendor data into ERP | 7 days | 21 November 2023 08:00 | 29 November 2023 17:00 |  | FGH,Tech M
349 | Yes | Auto Scheduled | Performance Testing | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
350 | Yes | Auto Scheduled | Performance testing set up and testing | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
351 | Yes | Auto Scheduled | Performance Testing Tool finalization and procurement | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
352 | Yes | Auto Scheduled | Resource allocation & Tool Training and walkthrough | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
353 | Yes | Auto Scheduled | Environment Provisioning | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
354 | Yes | Auto Scheduled | Expected Volume of users and Data | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
355 | Yes | Auto Scheduled | Workload | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
356 | Yes | Auto Scheduled | Critical Business Scenarios and script writing | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
357 | Yes | Auto Scheduled | Quick load and Distrubution of load across systems | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
358 | Yes | Auto Scheduled | Test Data | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
359 | Yes | Auto Scheduled | Ramp up | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
360 | Yes | Auto Scheduled | Steady State | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
361 | Yes | Auto Scheduled | Benchmarking Details | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
362 | Yes | Auto Scheduled | Load Test setup | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
363 | Yes | Auto Scheduled | Load testing | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
364 | Yes | Auto Scheduled | Distributed Load Testing | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
365 | Yes | Auto Scheduled | Acceptance Crteria | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
366 | Yes | Auto Scheduled | Load test scripts | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
367 | Yes | Auto Scheduled | Process Intensive test | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
368 | Yes | Auto Scheduled | Integrated third party system | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
369 | Yes | Auto Scheduled | Real Time transaction service | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
370 | Yes | Auto Scheduled | Submission | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
371 | Yes | Auto Scheduled | Review | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
372 | Yes | Auto Scheduled | Signoff | 40 days | 21 March 2024 08:00 | 15 May 2024 17:00
373 | Yes | Auto Scheduled | Training | 40 days | 01 April 2024 08:00 | 24 May 2024 17:00
374 | Yes | Auto Scheduled | Setting up the plan for Functional and non functional Training | 2 days | 01 April 2024 08:00 | 02 April 2024 17:00
375 | Yes | Auto Scheduled | Agenda for Trainings | 1 day | 03 April 2024 08:00 | 03 April 2024 17:00 | 374
376 | Yes | Auto Scheduled | Preparation for Training Material | 15 days | 04 April 2024 08:00 | 24 April 2024 17:00 | 375
377 | Yes | Auto Scheduled | Identify the Super Users for training | 2 days | 25 April 2024 08:00 | 26 April 2024 17:00 | 376
378 | Yes | Auto Scheduled | Communication and booking slot for Training | 1 day | 29 April 2024 08:00 | 29 April 2024 17:00 | 377
379 | Yes | Auto Scheduled | Imparting Training to Super users | 13 days | 29 April 2024 08:00 | 15 May 2024 17:00
380 | Yes | Auto Scheduled | Sharing the Training document | 1 day | 29 April 2024 08:00 | 29 April 2024 17:00 | 377
381 | Yes | Auto Scheduled | Product Information Management | 2 days | 30 April 2024 08:00 | 01 May 2024 17:00 | 380
382 | Yes | Auto Scheduled | Inventory Management | 2 days | 02 May 2024 08:00 | 03 May 2024 17:00 | 381
383 | Yes | Auto Scheduled | Customer Master | 2 days | 06 May 2024 08:00 | 07 May 2024 17:00 | 382
384 | Yes | Auto Scheduled | Sales Order Management | 2 days | 08 May 2024 08:00 | 09 May 2024 17:00 | 383
385 | Yes | Auto Scheduled | Vendor Master and Procurement and sourcing | 2 days | 10 May 2024 08:00 | 13 May 2024 17:00 | 384
386 | Yes | Auto Scheduled | Physical and Financial Postings | 2 days | 14 May 2024 08:00 | 15 May 2024 17:00 | 385
387 | Yes | Auto Scheduled | Training end users by Super users | 5 days | 16 May 2024 08:00 | 22 May 2024 17:00 | 386
388 | Yes | Auto Scheduled | Training Non Functional task | 1 day | 23 May 2024 08:00 | 23 May 2024 17:00 | 387
389 | Yes | Auto Scheduled | Sign off | 1 day | 24 May 2024 08:00 | 24 May 2024 17:00 | 388
390 | Yes | Auto Scheduled | UAT | 80 days | 05 February 2024 08:00 | 24 May 2024 17:00
391 | Yes | Auto Scheduled | UAT Tasks | 80 days | 05 February 2024 08:00 | 24 May 2024 17:00
392 | Yes | Auto Scheduled | UAT test scripts | 50 days | 05 February 2024 08:00 | 12 April 2024 17:00 | 322 | FGH
393 | Yes | Auto Scheduled | Test data | 5 days | 15 April 2024 08:00 | 19 April 2024 17:00 | 392 | FGH
394 | Yes | Auto Scheduled | Refresher training for super users | 2 days | 22 April 2024 08:00 | 23 April 2024 17:00 | 393 | FGH
395 | Yes | Auto Scheduled | Perform UAT | 15 days | 24 April 2024 08:00 | 14 May 2024 17:00 | 394 | FGH
396 | Yes | Auto Scheduled | Provide UAT support | 15 days | 29 April 2024 08:00 | 17 May 2024 17:00 | 395SS+3d | Tech M
397 | Yes | Auto Scheduled | UAT test result | 15 days | 01 May 2024 08:00 | 21 May 2024 17:00 | 395SS+5d | FGH
398 | Yes | Auto Scheduled | UAT test feedback implementation | 14 days | 06 May 2024 08:00 | 23 May 2024 17:00 | 395SS+8d | Tech M,FGH
399 | Yes | Auto Scheduled | UAT Sign off | 1 day | 24 May 2024 08:00 | 24 May 2024 17:00 | 398 | FGH
400 | Yes | Auto Scheduled | Complete the UAT Phase | 1 day | 24 May 2024 08:00 | 24 May 2024 17:00 | 398
401 | Yes | Auto Scheduled | Cutover Plan | 4 days | 20 May 2024 08:00 | 23 May 2024 17:00
402 | Yes | Auto Scheduled | Cutover plan preparation | 3 days | 20 May 2024 08:00 | 22 May 2024 17:00
403 | Yes | Auto Scheduled | Cutover walkthrough and update | 1 day | 23 May 2024 08:00 | 23 May 2024 17:00 | 402
404 | Yes | Auto Scheduled | Cutover pla sign off | 1 day | 23 May 2024 08:00 | 23 May 2024 17:00 | 402
405 | Yes | Auto Scheduled | Cutover and Implementation | 18 days | 24 May 2024 08:00 | 18 June 2024 17:00
406 | Yes | Auto Scheduled | Pre-Prod Task | 18 days | 24 May 2024 08:00 | 18 June 2024 17:00
407 | Yes | Auto Scheduled | SBR Go Live asseement workshop | 5 days | 24 May 2024 08:00 | 30 May 2024 17:00 |  | Tech M
408 | Yes | Auto Scheduled | Preparation | 3 days | 24 May 2024 08:00 | 28 May 2024 17:00 | 398 | Tech M,MS
409 | Yes | Auto Scheduled | walkthrough | 1 day | 29 May 2024 08:00 | 29 May 2024 17:00 | 408 | MS,Tech M
410 | Yes | Auto Scheduled | feedbback and updates | 1 day | 30 May 2024 08:00 | 30 May 2024 17:00 | 409
411 | Yes | Auto Scheduled | Golden Branch Configuration Verification. | 2 days | 27 May 2024 08:00 | 28 May 2024 17:00 | 400
412 | Yes | Auto Scheduled | FGH to provide Master and Transaction data | 2 days | 29 May 2024 08:00 | 30 May 2024 17:00 | 411
413 | Yes | Auto Scheduled | Verify data | 1 day | 31 May 2024 08:00 | 31 May 2024 17:00 | 412
414 | Yes | Auto Scheduled | Feedback and finalization of data | 1 day | 03 June 2024 08:00 | 03 June 2024 17:00 | 413
415 | Yes | Auto Scheduled | Upload Data Master and Transaction data | 1 day | 04 June 2024 08:00 | 04 June 2024 17:00 | 414
416 | Yes | Auto Scheduled | Vendor, product and Customer master | 1 day | 05 June 2024 08:00 | 05 June 2024 17:00 | 415
417 | Yes | Auto Scheduled | Transactions data | 1 day | 06 June 2024 08:00 | 06 June 2024 17:00 | 416
418 | Yes | Auto Scheduled | Validate Data | 1 day | 07 June 2024 08:00 | 07 June 2024 17:00 | 417
419 | Yes | Auto Scheduled | Feedback and Finalize Data | 1 day | 10 June 2024 08:00 | 10 June 2024 17:00 | 418
420 | Yes | Auto Scheduled | User verifications on cut over activities | 1 day | 11 June 2024 08:00 | 11 June 2024 17:00 | 419
421 | Yes | Auto Scheduled | FGH to provide Closing Balance | 1 day | 12 June 2024 08:00 | 12 June 2024 17:00 | 420
422 | Yes | Auto Scheduled | Closing Balance Transactions data | 1 day | 13 June 2024 08:00 | 13 June 2024 17:00 | 421
423 | Yes | Auto Scheduled | Validate Data | 1 day | 14 June 2024 08:00 | 14 June 2024 17:00 | 422
424 | Yes | Auto Scheduled | Feedback and Finalize Data | 1 day | 17 June 2024 08:00 | 17 June 2024 17:00 | 423
425 | Yes | Auto Scheduled | FGH Sign off on pre-Cut over activities | 1 day | 18 June 2024 08:00 | 18 June 2024 17:00 | 424
426 | Yes | Auto Scheduled | SBR Go Live re-assessment | 8 days | 31 May 2024 08:00 | 11 June 2024 17:00
427 | Yes | Auto Scheduled | SBR Go Live assessment Workshop preparation | 3 days | 31 May 2024 08:00 | 04 June 2024 17:00 | 410
428 | Yes | Auto Scheduled | SBR workshop | 1 day | 05 June 2024 08:00 | 05 June 2024 17:00 | 427
429 | Yes | Auto Scheduled | SBR workshop feedback implementation | 3 days | 06 June 2024 08:00 | 10 June 2024 17:00 | 428
430 | Yes | Auto Scheduled | SBR Go Live assessment Review and Sign off | 1 day | 11 June 2024 08:00 | 11 June 2024 17:00 | 429
431 | Yes | Auto Scheduled | Mock Dry Run - 1 | 9 days | 19 June 2024 08:00 | 01 July 2024 17:00
432 | Yes | Auto Scheduled | Test site is built as copy of Prod site | 3 days | 19 June 2024 08:00 | 21 June 2024 17:00 | 425
433 | Yes | Auto Scheduled | Apply manual configuration | 3 days | 24 June 2024 08:00 | 26 June 2024 17:00 | 432
434 | Yes | Auto Scheduled | Perform the data loads | 2 days | 27 June 2024 08:00 | 28 June 2024 17:00 | 433
435 | Yes | Auto Scheduled | Execute the cut-over | 1 day | 01 July 2024 08:00 | 01 July 2024 17:00 | 434
436 | Yes | Auto Scheduled | Go live Activities | 9 days | 01 July 2024 08:00 | 11 July 2024 17:00
437 | Yes | Auto Scheduled | Production movement approval | 1 day | 01 July 2024 08:00 | 01 July 2024 17:00 | 434
438 | Yes | Auto Scheduled | Final Production Data Migration | 2 days | 02 July 2024 08:00 | 03 July 2024 17:00 | 437
439 | Yes | Auto Scheduled | Data migration Validation in accordance with Company’s requirements (including opening balances and master data) | 1 day | 04 July 2024 08:00 | 04 July 2024 17:00 | 438
440 | Yes | Auto Scheduled | Integrations verifications (including to banks and all required Applications) | 1 day | 04 July 2024 08:00 | 04 July 2024 17:00 | 438
441 | Yes | Auto Scheduled | Deployment signoff | 1 day | 04 July 2024 08:00 | 04 July 2024 17:00 | 438
442 | Yes | Auto Scheduled | Gold environment deployment | 1 day | 05 July 2024 08:00 | 05 July 2024 17:00 | 441
443 | Yes | Auto Scheduled | Source code, Software artifacts (including object code) and related documentation for all Software | 1 day | 08 July 2024 08:00 | 08 July 2024 17:00 | 442
444 | Yes | Auto Scheduled | Deploy all functionality into production | 1 day | 08 July 2024 08:00 | 08 July 2024 17:00 | 442
445 | Yes | Auto Scheduled | Migrate solution to gold and production | 2 days | 09 July 2024 08:00 | 10 July 2024 17:00 | 444
446 | Yes | Auto Scheduled | Complete Deployment (Go-Live) | 1 day | 11 July 2024 08:00 | 11 July 2024 17:00 | 445
447 | Yes | Auto Scheduled | Hypercare- Steady State | 30 days | 12 July 2024 08:00 | 22 August 2024 17:00 | 446
448 | Yes | Auto Scheduled | FGH SCM Implementation Project Closure | 1 day | 23 August 2024 08:00 | 23 August 2024 17:00 | 447
449 | Yes | Manually Scheduled | <New Task>
450 | Yes | Manually Scheduled | <New Task>
451 | Yes | Auto Scheduled | FGH - Business Change | 1 day? | 10 June 2022 08:00 | 10 June 2022 17:00
452 | Yes | Manually Scheduled | Change Impact Analysis | 0 days | 10 June 2022 08:00 | 10 June 2022 08:00
453 | Yes | Manually Scheduled | Change impact Assessment
454 | Yes | Manually Scheduled | Training Approach/Strategy
455 | Yes | Manually Scheduled | Comms Approach/Strategy
456 | Yes | Manually Scheduled | Identify Key Stakeholders
457 | Yes | Manually Scheduled | Training | 0 days | 10 June 2022 08:00 | 10 June 2022 08:00
458 | Yes | Manually Scheduled | Create training materials
459 | Yes | Manually Scheduled | Orgainse training
460 | Yes | Manually Scheduled | Execute Training
461 | Yes | Manually Scheduled | Lessons Learnt feedback
462 | Yes | Manually Scheduled | Comms | 0 days | 10 June 2022 08:00 | 10 June 2022 08:00
463 | Yes | Manually Scheduled | Comms Plan
464 | Yes | Manually Scheduled | Create Comms Materials
465 | Yes | Manually Scheduled | Orgainse Comms sessions
466 | Yes | Manually Scheduled | Execute Comms
467 | Yes | Manually Scheduled | Leadership
468 | Yes | Auto Scheduled | M/S SBR Deliverables | 155 days? | 10 June 2022 08:00 | 12 January 2023 17:00
469 | Yes | Manually Scheduled | Environment Strategy
470 | Yes | Manually Scheduled | Integration Strategy
471 | Yes | Manually Scheduled | Data Migration Strategy
472 | Yes | Manually Scheduled | SBR Review | 155 days? | 10 June 2022 08:00 | 12 January 2023 17:00
473 | Yes | Auto Scheduled | SBR Process Strategy Creations | 6 days? | 26 December 2022 08:00 | 02 January 2023 17:00
474 | Yes | Auto Scheduled | Program Strategy | 1 day? | 26 December 2022 08:00 | 26 December 2022 17:00 |  | Tech M
475 | Yes | Auto Scheduled | Test Strategy | 1 day? | 27 December 2022 08:00 | 27 December 2022 17:00 | 474 | Tech M
476 | Yes | Auto Scheduled | Business Process Strategy | 1 day? | 27 December 2022 08:00 | 27 December 2022 17:00 | 474 | Tech M
477 | Yes | Auto Scheduled | Application Strategy | 1 day? | 28 December 2022 08:00 | 28 December 2022 17:00 | 475 | Tech M
478 | Yes | Auto Scheduled | Data Strategy | 1 day? | 28 December 2022 08:00 | 28 December 2022 17:00 | 475 | Tech M
479 | Yes | Auto Scheduled | Integration Strategy | 1 day? | 29 December 2022 08:00 | 29 December 2022 17:00 | 477 | Tech M
480 | Yes | Auto Scheduled | Intelligence Strategy | 1 day? | 29 December 2022 08:00 | 29 December 2022 17:00 | 477 | Tech M
481 | Yes | Auto Scheduled | Security Strategy | 1 day? | 30 December 2022 08:00 | 30 December 2022 17:00 | 479 | Tech M
482 | Yes | Auto Scheduled | Application Lifecycle Management Strategy | 1 day? | 30 December 2022 08:00 | 30 December 2022 17:00 | 479 | Tech M
483 | Yes | Auto Scheduled | Environment and Capcity Strategy | 1 day? | 02 January 2023 08:00 | 02 January 2023 17:00 | 482 | Tech M
484 | Yes | Auto Scheduled | SBR Process Strategy Submission | 2 days | 03 January 2023 08:00 | 04 January 2023 17:00 | 483 | Tech M
485 | Yes | Auto Scheduled | SBR Process walk through and feedback implementation | 1 day | 05 January 2023 08:00 | 05 January 2023 17:00 | 484 | Tech M,FGH/MS
486 | Yes | Auto Scheduled | SBR process sign off | 5 days | 06 January 2023 08:00 | 12 January 2023 17:00 | 485 | MS
487 | Yes | Auto Scheduled | Arch Deliverables | 5 days? | 10 June 2022 08:00 | 16 June 2022 17:00
488 | Yes | Auto Scheduled | As-is Business Process | 5 days? | 10 June 2022 08:00 | 16 June 2022 17:00
489 | Yes | Manually Scheduled | Draft
490 | Yes | Manually Scheduled | Review | 5 days
491 | Yes | Manually Scheduled | Approval | 1 day