## Sheet1
ID | Outline_Level | Name | Start_Date | Duration | Finish_Date
P5 | 1 | Barclays Accreditation (Discovery) | 3 November 2025 00:00 | 150 days | 31 May 2026 00:00
P6 | 1 | Data Audit( incldg cookie/consent management) | 20 October 2025 00:00 | 226 days | 31 August 2026 00:00
P2 | 1 | Web App Modernization PII (Back End) | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P3 | 1 | BNPL - 6 mths existing eligible customers | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P1 | 1 | Search Engine Optimisation | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P4 | 1 | Financier Archival and Erasure (Discovery) | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P8 | 1 | Financier Core Release | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P7 | 1 | Credit Decisioning - Account Management | 20 October 2025 00:00 | 226 days | 31 August 2026 00:00
P15 | 1 | ecomm customer data auditing | 3 November 2025 00:00 | 150 days | 31 May 2026 00:00
P11 | 1 | Dec Alpha C++ | 4 May 2026 00:00 | 151 days | 30 November 2026 00:00
P12 | 1 | Trend Antispam replacement | 4 May 2026 00:00 | 151 days | 30 November 2026 00:00
P14 | 1 | LDAP Replacement | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P13 | 1 | F5 WAF Upgrade | 16 February 2026 00:00 | 75 days | 31 May 2026 00:00
P18 | 1 | Adobe Campaign review | 21 July 2025 00:00 | 225 days | 31 May 2026 00:00
P17 | 1 | Document Scanning | 20 October 2025 00:00 | 226 days | 31 August 2026 00:00
P22 | 1 | Retail Media and Sponsored Product Integration | 16 February 2026 00:00 | 75 days | 31 May 2026 00:00
P21 | 1 | FGH as a seller (Dropship/Marketplace) | 19 January 2026 00:00 | 226 days | 30 November 2026 00:00
P30 | 1 | AI-Led Content Gap Analysis/Range Optimisation | 4 May 2026 00:00 | 151 days | 30 November 2026 00:00
P29 | 1 | Lily AI PII (Internal Search) | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P20 | 1 | B2B - Asda | 21 July 2025 00:00 | 225 days | 31 May 2026 00:00
P23 | 1 | Remove Courier Collections for Returns | 18 May 2026 00:00 | 76 days | 31 August 2026 00:00
P24 | 1 | Kaleidoscope (reinvest) | 3 August 2026 00:00 | 150 days | 28 February 2027 00:00
P27 | 1 | Own Buy Expansion | 17 August 2026 00:00 | 76 days | 30 November 2026 00:00
P28 | 1 | Fragrance Model | 18 May 2026 00:00 | 76 days | 31 August 2026 00:00
P10 | 1 | Server Side Anaytics | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P19 | 1 | Technology Development (HR training Platform) | 16 February 2026 00:00 | 75 days | 31 May 2026 00:00
P32 | 1 | Trade Place | 18 May 2026 00:00 | 76 days | 31 August 2026 00:00
P33 | 1 | Digital downloads | 17 August 2026 00:00 | 76 days | 30 November 2026 00:00
P34 | 1 | Profit-Based Bidding (PBB) | 2 February 2026 00:00 | 151 days | 31 August 2026 00:00
P35 | 1 | Additional Payments (Apple pay/Google Pay) | 4 May 2026 00:00 | 151 days | 30 November 2026 00:00
P36 | 1 | AI-Driven Product Data Enrichment (STM Phase 2) | 17 August 2026 00:00 | 76 days | 30 November 2026 00:00
P98 | 1 | Develop order tracking links in MyAccount to link directly to carrier ie Evri for the latest view and support options | 16 February 2026 00:00 | 75 days | 31 May 2026 00:00