## Sheet1
ID | Outline_Level | Name | Start_Date | Duration | Finish_Date
5 | 1 | Barclays Accreditation (Discovery) | 2025-11-03 | 150 | 2026-05-31
6 | 1 | Data Audit( incldg cookie/consent management) | 2025-10-20 | 226 | 2026-08-31
2 | 1 | Web App Modernization PII (Back End) | 2026-02-02 | 151 | 2026-08-31
3 | 1 | BNPL - 6 mths existing eligible customers | 2026-02-02 | 151 | 2026-08-31
1 | 1 | Search Engine Optimisation | 2026-02-02 | 151 | 2026-08-31
4 | 1 | Financier Archival and Erasure (Discovery) | 2026-02-02 | 151 | 2026-08-31
8 | 1 | Financier Core Release | 2026-02-02 | 151 | 2026-08-31
7 | 1 | Credit Decisioning - Account Management | 2025-10-20 | 226 | 2026-08-31
15 | 1 | ecomm customer data auditing | 2025-11-03 | 150 | 2026-05-31
11 | 1 | Dec Alpha C++ | 2026-05-04 | 151 | 2026-11-30
12 | 1 | Trend Antispam replacement | 2026-05-04 | 151 | 2026-11-30
14 | 1 | LDAP Replacement | 2026-02-02 | 151 | 2026-08-31
13 | 1 | F5 WAF Upgrade | 2026-02-16 | 75 | 2026-05-31
18 | 1 | Adobe Campaign review | 2025-07-21 | 225 | 2026-05-31
17 | 1 | Document Scanning | 2025-10-20 | 226 | 2026-08-31
22 | 1 | Retail Media and Sponsored Product Integration | 2026-02-16 | 75 | 2026-05-31
21 | 1 | FGH as a seller (Dropship/Marketplace) | 2026-01-19 | 226 | 2026-11-30
30 | 1 | AI-Led Content Gap Analysis/Range Optimisation | 2026-05-04 | 151 | 2026-11-30
29 | 1 | Lily AI PII (Internal Search) | 2026-02-02 | 151 | 2026-08-31
20 | 1 | B2B - Asda | 2025-07-21 | 225 | 2026-05-31
23 | 1 | Remove Courier Collections for Returns | 2026-05-18 | 76 | 2026-08-31
24 | 1 | Kaleidoscope (reinvest) | 2026-08-03 | 150 | 2027-02-28
25 | 1 | Freemans New Customer Investment | Not Mapped | 1 | 2027-02-28
26 | 1 | Credit Headroom and DPO | Not Mapped | 1 | 2026-08-31
27 | 1 | Own Buy Expansion | 2026-08-17 | 76 | 2026-11-30
28 | 1 | Fragrance Model | 2026-05-18 | 76 | 2026-08-31
10 | 1 | Server Side Anaytics | 2026-02-02 | 151 | 2026-08-31
19 | 1 | Technology Development (HR training Platform) | 2026-02-16 | 75 | 2026-05-31
0 | 1 | yyy | Not Mapped | 1 | Not Mapped
32 | 1 | Trade Place | 2026-05-18 | 76 | 2026-08-31
33 | 1 | Digital downloads | 2026-08-17 | 76 | 2026-11-30
34 | 1 | Profit-Based Bidding (PBB) | 2026-02-02 | 151 | 2026-08-31
35 | 1 | Additional Payments (Apple pay/Google Pay) | 2026-05-04 | 151 | 2026-11-30
36 | 1 | AI-Driven Product Data Enrichment (STM Phase 2) | 2026-08-17 | 76 | 2026-11-30
0 | 1 | Develop order tracking links in MyAccount to link directly to carrier ie Evri for the latest view and support options | 2026-02-16 | 75 | 2026-05-31
0 | 1 | xxx | Not Mapped | 1 | Not Mapped
39 | 1 | WMS Replacement | Not Mapped | 1 | Not Mapped